## ToJune2015
Best Case Timeline up to June 2015
| 2015-02-28 | 2015-03-31 | 2015-04-30 | 2015-05-31 | 2015-06-30
Testing
NTIA review
ICG assessment of IETF and RIR proposals (Step I*)
IETF engagement on ICG Assessment Step I, if necessary
RIRs engagement on ICG Assessment Step I, if necessary
Draft proposal production, IETF+RIRs (Step II)
IETF engagement on draft proposal (Step II), if necessary
RIRs engagement on draft proposal (Step II), if necessary
Draft IETF+RIRs proposal published
CWG proposal development
ICANN 53
Legend
ICG
IETF
RIRs
CWG
NTIA
All interested parties
ICANN meetings
*Step I and Step II refer to ICG proposal finalization process steps.

## AfterNames
Best Case Timeline after Receipt of Names CWG Proposal
| Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9
Testing
NTIA review
CWG delivery of proposal to ICG
ICG Assessment of CWG proposal (Step I*)
Draft proposal production, complete proposal (Step II)
CWG engagement on ICG Assessment Step I, if necessary
CWG engagement on draft proposal (Step II), if necessary
IETF engagement on draft proposal (Step II), if necessary
RIRs engagement on draft proposal (Step II), if necessary
ICANN 54
Draft complete proposal published
Public comment on draft proposal
ICG assessment of public comments
IETF engagement on public comments, if necessary
RIRs engagement on public comments, if necessary
CWG engagement on public comments, if necessary
ICANN 55
ICG transmission of final proposal to ICANN Board
Legend
ICG
IETF
RIRs
CWG
NTIA
All interested parties
ICANN meetings
*Step I and Step II refer to ICG proposal finalization process steps.