Timeline Discussion

At the inaugural meeting of the IANA Stewardship Coordination Group (ICG), there was a discussion of the timeline to produce a proposal for delivery to the NTIA.  An aggressive goal is for the transition to take place in September 2015.  The whole Internet community has a role in the development and review of the proposal, and this aggressive timeline is provided for review and comment.

Step 0:	Request for Communities to produce proposal text – now

The ICG believes that the names, numbers, and protocol parameters communities have already this work using their own processes.  The ICG plans to publish a detailed call for responses from all communities on or before 31 Jul 2014.

Step 1:	Communities' work – now to 30 Jan 2015

Communities develop and complete their responses. Use of open and transparent processes will allow other communities to continuously review progress.

Decision:	Is the aggressive schedule being met? – by 2 Feb 2015

If the contributions from the communities have arrived, then proceed with the aggressive timeline. Otherwise, develop a revised timeline.

Step 2:	Coordination and alignment – wrap up by 27 Feb 2015

Stitch together the contributions from the communities, publishing a strawman proposal and a companion analysis document.  Seek review and comments from all communities, the global Internet community, and NTIA.

Begin testing (Step 4) if the analysis of the strawman proposal shows few gaps.

Step 3:	Community review – wrap up by 29 May 2015

Communities resolve identified gaps and update their responses based on received comments, and the ICG produces the final proposal.  Comments from NTIA are strongly desired.

Step 4:	Testing – wrap up by 26 Jun 2015

Demonstrate that the system can run as proposed.

Decision:	Is the proposal ready? – by 30 Jun 2015

Does the community have consensus on the proposal content?  Has testing shown the system is working?  If so, deliver proposal to ICANN Board for delivery to NTIA.  If not, develop a revised timeline.

Step 5:	NTIA evaluation and approval – wrap up by 30 Sep 2015

NTIA does whatever they need to do with the proposal.  It is unknown how much time will be needed, but we should expect several months.