Latin Generation Panel (GP) Meeting

Notes from meeting on 5 April 2018

Meeting Attendees (in alphabetical order)

WG members:

- Bill Jouris

- Dennis T. Tanaka

- Hazem Hezzah

- Mats Dufberg

- Mirjana Tasić

Staff:

- Pitinan Kooarmornpatana

- Sarmad Hussain

Meeting Notes

The GP discussed the following agenda items:

- Code point repertoire table. The WG finalized and accepted the reference indexing in the repertoire table prepared by ICANN staff.

- Letter to the community calling for the information for variant. The GP discussed that there are two target audiences; GP members and non-GP members which could be general users or national or regional linguistic organizations. It was agreed that the message should be simple. It should inform readers about the context of the work and request for information of any interchangeable characters in their language. ICANN staff could assist to circulate the message to relevant organizations and keep track of the responses.

- Principals for variant analysis.  The chair requested all members to review the current draft to fill in the suggestions to be finalized in the next call.

- Status of the Drafting WG. It was agreed that the finalized repertoire would be added when the proposal is nearly completed, to prevent unintended changes in the table. The GP requested ICANN staff to adjust the repertoire table to be sorted ascendingly by Unicode code. The GP planed that the first draft proposal to accompany the repertoire xml will be ready to send to the IP in two weeks.

- AOB. The chair request for the alternate online meeting tool for the next meeting. The tool should provide the screen sharing, chat window and the speaker queue feature.

Action Items

| S. No. | Action Items | Owner |
| --- | --- | --- |
| 1 | Simplify the letter to the community calling for the information for variant. | DT |
| 2 | Review the draft Principle for variant analysis and add the special cases section. | ALL |
| 3 | Adjust the repertoire table in the Unicode code ascending order. | SH |
| 4 | Complete the first draft of proposal to accompany the repertoire XML. | MT |
| 5 | Work with the GP chair to decide the tool for the next meeting. | PK |