## Sheet1
Task name | By | Status | Note
Develop call for participation | Tue 06-23-15 | Done
Publicly release call for participation | Fri 07-24-15 | Done
Meeting | Tue 9-22-15 | Done
Face-to-face meeting (Dublin) | Sun 10-18-15 | Done
Meeting on character set | Tue 11-10-15 | Done
Invitation to experts to ensure diversity | Fri 11-20-15 | In progress | e.g., Vietnamese and African
Meeting on character set | Tue 11-24-15 | Done
Meeting on character set | Tue 12-08-15 | Done
Meeting on panel-formation proposal | Tue 01-05-16
Meeting on panel-formation proposal | Tue 01-19-16
Meeting on panel-formation proposal | Tue 02-02-16
Meeting on finalization of membership | Tue 02-16-16
Proposal finalization | Fri 02-19-16
Application to ICANN for formation of LGP | Fri 02-26-16 |  | If this is not possible, more time/advisor(s) may be needed.
Meeting | Tue 03-01-16
Face-to-face meeting (Marrakech) | Sun 03-06-16 |  | Or soon after. Also interaction with IP.
Meeting on character set | Tue 03-22-16
Meeting on character set | Tue 04-12-16
Meeting on general principles for inclusion | Tue 04-26-16
Meeting on general principles for exclusion | Tue 05-10-16
Meeting on general principles for deferral | Tue 05-24-16 |  | An intersessional meeting may be necessary to work on the character set.
Release of character set for public comment | Tue 06-07-16
Meeting | Tue 06-21-16
Face-to-face meeting (Panama) | Mon 06-27-16 |  | Or soon after. Also interaction with IP.
Meeting on finalizaton of character set | Tue 07-12-16
Meeting: Discussion on variants | Tue 07-26-16 |  | If we were to require only cross-script variants, this could be shorter.
Meeting: Do we need in-script variants? | Tue 08-09-16
Meeting: Do we need cross-script variants? | Tue 08-30-16
Meeting | Tue 09-13-16
Meeting on finalization of variants | Tue 09-27-16
Meeting: Release of variants for public comment | Tue 10-25-16
Face-to-face meeting (Puerto Rico) | Sun 10-29-16 |  | Or soon after. Also interaction with IP.
Incorporation of comments from public and IG | Tue 11-29-16
Finalization of variants | Tue 12-13-16
Discussion of Whole Label Rules | Tue 01-10-17
Documenting Whole Label Rules | Tue 01-24-17
Meeting | Tue 02-07-17
Meeting on finalization of Whole Label Rules | Tue 02-21-17
Release of Whole Label Rules for public comment | Tue 03-07-17
Face-to-face meeting (Europe) | Sun 03-12-17 |  | Or soon after. Also interaction with IP.
Incorporation of comments from public and IG | Tues 03-21-17
Finalize document | Tues 04-04-17
Meeting | Tues 04-18-17
Finalize LGR XML structure | Tues 05-02-17
Final edits | Tues 05-16-17
Submission to ICANN | Tues 05-30-17