## Sheet1
LGR for Neo-Brahmi GP
No. of days | 742
Start Date | 2015-01-15
End Date | 2017-01-26
Task | Duration | Start Date | End Date
Finalization of Membership | 7 | 2015-01-15 | 2015-01-21
Evaluation of Applicants and Finalization | 7 | 2015-01-15 | 2015-01-21
Formation of Generation Panel
Introduce Members | 130 | 2015-01-22 | 2015-05-31
Discussion and Finalization of Proposal
Application to ICANN for formation of Neo-Brahmi GP for creation of Neo-Brahmi LGR for Root Zone
Interaction within Neo-Brahmi GP | 10 | 2015-06-01 | 2015-06-10
Meeting with Chair
Meeting for Devanagari, Gujarati, Punjabi script members
Meeting for Bengali script members
Meeting for Tamil, Telugu script members
This phase was over with the first Face to Face meeting of the group on 16th July 2015
As per the discussions during the meeting, some additional members were to be invited to complete the full language representation
Two additional months were factored-in for the same.
Character Set
Definition of General principles
For inclusion | 60 | 2015-09-22 | 2015-11-20
For Exclusion
For Deferral
Interaction with IG for Feedback | 15 | 2015-11-21 | 2015-12-05
Finalization of character sets
Included in Neo-Brahmi Scripts IDNs | 30 | 2015-12-06 | 2016-01-04
Excluded from Neo-Brahmi Scripts IDNs
Interaction with IG for feedback
Documenting Character Set on MSR
Release for Public Comments: | 40 | 2016-01-05 | 2016-02-13
Buffer time to take into account the Public comments and modifications, if any. | 15 | 2016-02-14 | 2016-02-28
Character sets for Neo-Brahmi Scripts LGR | 5 | 2016-02-29 | 2016-03-04
Variants
Definition of General principles | 30 | 2016-03-05 | 2016-04-03
Variant qualification
Typology of Variants
Interaction with IG for Feedback | 10 | 2016-04-04 | 2016-04-13
Analysis of Data | 30 | 2016-04-14 | 2016-05-13
Variants identification
Finalization of Variants with disposition
Documenting Variants on MSR
Release for Public Comment | 40 | 2016-05-13 | 2016-06-21
Incorporation of Comments by Public and IG | 15 | 2016-06-22 | 2016-07-06
Whole Label Rules
Definition of General principles | 30 | 2016-07-07 | 2016-08-05
Finalization of guiding principles
Interaction with IG for Feedback
Finalization of Rules | 60 | 2016-08-06 | 2016-10-04
Initial Analysis
Second Review of Label Rules
Finalization of Whole Label Rules
Documenting Whole Label Rules
Release for Public Comment: | 40 | 2016-10-05 | 2016-11-13
Incorporation of Comments by Public and IG | 15 | 2016-12-14 | 2016-12-28
Finalizing LGR Document | 30 | 2016-12-28 | 2017-01-26
Finalizing document
Finalizing LGR XML Structure
Submission to ICANN
Formulas:
End Date = SUM([Start Date],[Duration])-1