## RDS Workplan
Registration Directory Service (RDS) WHOIS2 Review Team (RDS-WHOIS2-RT) DRAFT WORKPLAN
Background The Registration Directory Service (RDS) WHOIS2 Review Team (RDS-WHOIS2-RT) was confirmed in June 2017 and held its first Plenary meeting in July 2017. This document serves as a guide developed by the RDS-WHOIS2-RT as a plan for its work for the review focusing on key areas for discussion and milestones to be achieved during the review process and it will be updated as the work progresses. Dates reflect a typical Review lifecycle, but are to be adjusted by the Review Team, based upon their agreed-upon scope and the effort required to address highest-priority objectives within available budget and time.
At Risk | Task Name | Start Date | End Date | Assigned To | Duration (days) | % Complete | Comments
| Assemble Review Team |  |  |  | 217 | 100%
| Appoint RDS-WHOIS2 Review Team | 2016-10-28 | 2017-06-02 | SO/AC Chairs | 217 | 100% | See https://www.icann.org/news/announcement-2017-06-02-en
| Plan Review |  |  |  | 225 | 40%
| Determine leadership | 2017-06-05 | 2017-10-03 | RDS-WHOIS2-RT | 120 | 50% | Interim leadership appointed on plenary call #3. Leadership to be confirmed at Brussels meeting
| Determine role of observers | 2017-07-13 | 2017-08-13 | RDS-WHOIS2-RT | 31 | 100% | Completed on plenary call #4
| Adopt legal docs (Conflict of Interest policy, NDA, Statement of Interest) | 2017-08-03 | 2017-09-14 | RDS-WHOIS2-RT | 42 | 30% | ICANN org to send drafts
| Develop methodology to prioritize issues to be addressed in scope, including validating issues against ICANN Bylaws | 2017-07-20 | 2017-09-14 | RDS-WHOIS2-RT | 56 | 80%
| Adopt a framework that identifies the prioritized focus of the work to be performed by the Review Team (Scope) | 2017-07-20 | 2017-10-03 | RDS-WHOIS2-RT | 75 | 80%
| Adopt and publish Terms of Reference | 2017-08-03 | 2017-11-24 | RDS-WHOIS2-RT | 113 | 80% | ICANN org provided a template for Review Team consideration.
| Adopt and publish Workplan | 2017-09-07 | 2017-11-24 | RDS-WHOIS2-RT | 78 | 0%
| Send adopted ToR and Work Plan to ICANN Board | 2017-10-20 | 2017-11-24 | RDS-WHOIS2-RT | 35 | 0%
| Define Review Team project management roles and responsibilities, including budget management | 2017-08-11 | 2017-10-03 | RDS-WHOIS2-RT | 53 | 100% | Discussed on leadership call #3 (August 11). To be confirmed by new/confirmed leadership
| Identify need for and deliver a proposal on division of work | 2017-07-20 | 2017-10-20 | RDS-WHOIS2-RT | 92 | 40%
| Develop and adopt outreach plan | 2017-10-20 | 2017-11-30 | RDS-WHOIS2-RT | 41 | 0% | ICANN org to provide a template for Review Team consideration
| Develop and adopt template for "First pass Planning Questions" | 2017-10-03 | 2017-10-31 | RDS-WHOIS2-RT | 28 | 0% | ICANN org to provide a template for Review Team consideration
| Develop and adopt template for findings and recommendations | 2018-01-02 | 2018-01-16 | RDS-WHOIS2-RT | 14 | 0% | ICANN org to provide a template for Review Team consideration
| Define structure of subgroups reports | 2018-01-02 | 2018-01-16 | RDS-WHOIS2-RT | 14 | 0% | ICANN org to provide a template for Review Team consideration
| Research and Studies |  |  |  | 240 | 30%
| Assemble repository of background materials | 2016-10-27 | 2018-01-31 | ICANN org | 461 | 50% | Available on dedicated wiki page. ICANN organization to continue populating, as requested
| Identify briefings / data sources needed | 2017-06-05 | 2018-01-31 | RDS-WHOIS2-RT | 240 | 40%
| Determine requirements for independent expert(s) and - if necessary - develop Statement of Work | 2017-10-03 | 2018-01-31 | RDS-WHOIS2-RT | 120 | 0%
| Conduct Review |  |  |  | 178 | 0%
Subteams
| WHOIS 1 Review Team Recommendations |  |  |  |  | 0%
| Administrative Duties |  |  |  |  | 0%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 1 | 17 | 0% | Using template referenced in row 19
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Identify briefings/data sources needed | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Adopt statement of work and associated work plan | 2017-11-03 | 2017-11-15 | Subgroup 1 | 12 | 0%
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-01-12 | Subgroup 1 | 84 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-01-16 | Subgroup 1 | 46 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-01-16 | 2018-01-30 | Subgroup 1 | 14 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Produce subgroup report for subgroup members' approval | 2018-02-12 | 2018-02-26 | Subgroup 1 | 14 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-02-26 | 2018-03-09 | Subgroup 1 | 11 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-03-09 | 2018-03-16 | Subgroup 1 | 7 | 0% | ICANN61 (San Juan: March 10-15)
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-03-10 | 2018-03-30 | Subgroup 1 | 20 | 0%
| Anything New |  |  |  |  | 0%
| Administrative Duties |  |  |  |  | 0%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 1 | 17 | 0% | Using template referenced in row 19
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Identify briefings/data sources needed | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Adopt statement of work and associated work plan | 2017-11-03 | 2017-11-15 | Subgroup 1 | 12 | 0%
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-01-12 | Subgroup 1 | 84 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-01-16 | Subgroup 1 | 46 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-01-16 | 2018-01-30 | Subgroup 1 | 14 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Produce subgroup report for subgroup members' approval | 2018-02-12 | 2018-02-26 | Subgroup 1 | 14 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-02-26 | 2018-03-09 | Subgroup 1 | 11 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-03-09 | 2018-03-16 | Subgroup 1 | 7 | 0% | ICANN61 (San Juan: March 10-15)
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-03-10 | 2018-03-30 | Subgroup 1 | 20 | 0%
| Law Enforcement Needs |  |  |  |  | 0%
| Administrative Duties |  |  |  |  | 0%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 1 | 17 | 0% | Using template referenced in row 19
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Identify briefings/data sources needed | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Adopt statement of work and associated work plan | 2017-11-03 | 2017-11-15 | Subgroup 1 | 12 | 0%
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-01-12 | Subgroup 1 | 84 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-01-16 | Subgroup 1 | 46 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-01-16 | 2018-01-30 | Subgroup 1 | 14 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Produce subgroup report for subgroup members' approval | 2018-02-12 | 2018-02-26 | Subgroup 1 | 14 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-02-26 | 2018-03-09 | Subgroup 1 | 11 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-03-09 | 2018-03-16 | Subgroup 1 | 7 | 0% | ICANN61 (San Juan: March 10-15)
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-03-10 | 2018-03-30 | Subgroup 1 | 20 | 0%
| Consumer Trust |  |  |  |  | 0%
| Administrative Duties |  |  |  |  | 0%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 1 | 17 | 0% | Using template referenced in row 19
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Identify briefings/data sources needed | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Adopt statement of work and associated work plan | 2017-11-03 | 2017-11-15 | Subgroup 1 | 12 | 0%
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-01-12 | Subgroup 1 | 84 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-01-16 | Subgroup 1 | 46 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-01-16 | 2018-01-30 | Subgroup 1 | 14 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Produce subgroup report for subgroup members' approval | 2018-02-12 | 2018-02-26 | Subgroup 1 | 14 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-02-26 | 2018-03-09 | Subgroup 1 | 11 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-03-09 | 2018-03-16 | Subgroup 1 | 7 | 0% | ICANN61 (San Juan: March 10-15)
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-03-10 | 2018-03-30 | Subgroup 1 | 20 | 0%
| Safeguard Registrant Data |  |  |  |  | 0%
| Administrative Duties |  |  |  |  | 0%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 1 | 17 | 0% | Using template referenced in row 19
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Identify briefings/data sources needed | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Adopt statement of work and associated work plan | 2017-11-03 | 2017-11-15 | Subgroup 1 | 12 | 0%
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-01-12 | Subgroup 1 | 84 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-01-16 | Subgroup 1 | 46 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-01-16 | 2018-01-30 | Subgroup 1 | 14 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Produce subgroup report for subgroup members' approval | 2018-02-12 | 2018-02-26 | Subgroup 1 | 14 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-02-26 | 2018-03-09 | Subgroup 1 | 11 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-03-09 | 2018-03-16 | Subgroup 1 | 7 | 0% | ICANN61 (San Juan: March 10-15)
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-03-10 | 2018-03-30 | Subgroup 1 | 20 | 0%
| Compliance |  |  |  |  | 0%
| Administrative Duties |  |  |  |  | 0%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 1 | 17 | 0%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2017-11-03 | Subgroup 1 | 31 | 0% | Using template referenced in row 19
| Identify briefings/data sources needed | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0% | Using template referenced in row 19
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2017-12-31 | Subgroup 1 | 89 | 0%
| Adopt statement of work and associated work plan | 2017-11-03 | 2017-11-15 | Subgroup 1 | 12 | 0%
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-01-12 | Subgroup 1 | 84 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-01-16 | Subgroup 1 | 74 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-01-16 | Subgroup 1 | 46 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-01-16 | 2018-01-30 | Subgroup 1 | 14 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-01-30 | 2018-02-12 | Subgroup 1 | 13 | 0%
| Produce subgroup report for subgroup members' approval | 2018-02-12 | 2018-02-26 | Subgroup 1 | 14 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-02-26 | 2018-03-09 | Subgroup 1 | 11 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-03-09 | 2018-03-16 | Subgroup 1 | 7 | 0% | ICANN61 (San Juan: March 10-15)
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-03-10 | 2018-03-30 | Subgroup 1 | 20 | 0%
Review Team
| Draft Report |  |  |  | 269 | 0%
| Administrative Duties |  |  |  |  | 0%
| Adopt report format | 2018-01-02 | 2018-01-16 | RDS-WHOIS2 Team | 14 | 0%
| Internal Review |  |  |  |  | 0%
| Provide input on subgroups' Draft Report sections | 2018-03-09 | 2018-04-27 | RDS-WHOIS2 Team | 49 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-03-09 | 2018-04-27 | RDS-WHOIS2 Team | 49 | 0%
| Pre-approve draft recommendations | 2018-04-27 | 2018-05-18 | RDS-WHOIS2 Team | 21 | 0%
| Outreach |  |  |  |  | 0%
| Seek Board Caucus group and ICANN organization’s input on implementability of draft recommendations | 2018-06-01 | 2018-06-28 | RDS-WHOIS2 Team | 27 | 0%
| Seek Community’s input on implementability of draft recommendations | 2018-06-25 | 2018-06-28 | RDS-WHOIS2 Team | 3 | 0% | ICANN 62 (25-28 June 2018)
| Assembling Draft Report |  |  |  |  | 0%
| Produce Draft Report | 2018-04-27 | 2018-07-20 | RDS-WHOIS2 Team | 84 | 0%
| Approval process |  |  |  |  | 0%
| Approve draft findings and recommendations | 2018-05-18 | 2018-07-20 | RDS-WHOIS2 Team | 63 | 0%
| Approve draft report for public comment | 2018-07-20 | 2018-07-31 | RDS-WHOIS2 Team | 11 | 0%
| Publishing Draft Report |  |  |  |  | 0%
| Send approved draft report sections to language services | 2018-05-18 | 2018-08-01 | ICANN org | 75 | 0% | As sections become available
| Public Comment and Outreach on Draft Report |  |  |  |  | 0%
| Publish draft report for public comment | 2018-08-01 | 2018-09-10 | ICANN org | 40 | 0%
| Socialize draft recommendations with community | 2018-08-01 | 2018-08-17 | RDS-WHOIS2 Team | 16 | 0% | Webinars
| Produce summary of public comments | 2018-09-10 | 2018-09-24 | ICANN org | 14 | 0%
| Adopt public comment summary for publication | 2018-09-24 | 2018-09-28 | RDS-WHOIS2 Team | 4 | 0%
| Final Report |  |  |  | 67 | 0%
| Updating Draft Report |  |  |  |  | 0%
| Assemble final recommendations and update draft report based on public comments received | 2018-09-28 | 2018-11-05 | RDS-WHOIS2 Team | 38 | 0%
| Cross-check final recommendations with scope and Bylaws | 2018-09-28 | 2018-11-05 | RDS-WHOIS2 Team | 38 | 0%
| Outreach |  |  |  |  | 0%
| Seek Community’s input on implementability of draft recommendations | 2018-10-19 | 2018-10-26 | RDS-WHOIS2 Team | 7 | 0% | ICANN63 (20-26 October 2018)
| Approval process |  |  |  |  | 0%
| Approve final findings, recommendations and report for Board consideration | 2018-10-26 | 2018-12-03 | RDS-WHOIS2 Team | 38 | 0%
| Send Final Report |  |  |  |  | 0%
| Send final report to ICANN Board | 2018-12-03 | 2018-12-04 | RDS-WHOIS2 Team | 1 | 0%
| Publish final report | 2018-12-03 | 2018-12-04 | ICANN org | 1 | 0%
| Send Final Report to language services | 2018-12-03 | 2018-12-04 | ICANN org | 1 | 0%
| Implementation planning and feedback |  |  |  | 70 | 0%
| Complete ICANN organization survey on review process | 2018-12-04 | 2019-01-04 | RDS-WHOIS2 Team | 31 | 0%
| Identify one or two Review Team Members to remain available for clarification as may be needed during the planning phase of implementation of Review Team Recommendations. | 2018-10-26 | 2018-12-03 | RDS-WHOIS2 Team | 38 | 0%
| Face to Face meetings |  |  |  |  | 25%
| #1 Brussels | 2017-10-02 | 2017-10-03 |  |  | 100%
| #2 ICANN 61 |  |  |  |  | 0%
| #3 ICANN 62 |  |  |  |  | 0%
| #4 ICANN 63 |  |  |  |  | 0%