## RDS Workplan
Registration Directory Service (RDS) WHOIS2 Review Team (RDS-WHOIS2-RT) DRAFT WORKPLAN
Background The Registration Directory Service (RDS) WHOIS2 Review Team (RDS-WHOIS2-RT) was confirmed in June 2017 and held its first Plenary meeting in July 2017. This document serves as a guide developed by the RDS-WHOIS2-RT as a plan for its work for the review focusing on key areas for discussion and milestones to be achieved during the review process and it will be updated as the work progresses. Dates reflect a typical Review lifecycle, but are to be adjusted by the Review Team, based upon their agreed-upon scope and the effort required to address highest-priority objectives within available budget and time.
At Risk | Task Name | Start Date | End Date | Assigned To | Duration (days) | % Complete | Comments
| Assemble Review Team |  |  |  | 217 | 100%
| Appoint RDS-WHOIS2 Review Team | 2016-10-28 | 2017-06-02 | SO/AC Chairs | 217 | 100% | See https://www.icann.org/news/announcement-2017-06-02-en
| Plan Review |  |  |  | 249 | 77.68%
| Administration |  |  |  |  | 92.5%
| Determine leadership | 2017-06-05 | 2017-10-03 | RDS-WHOIS2-RT | 120 | 100% | Completed in Brussels, 4 October 2017
| Determine role of observers | 2017-07-13 | 2017-08-13 | RDS-WHOIS2-RT | 31 | 100% | Completed on plenary call #4
| Adopt legal docs (Conflict of Interest policy, Statement of Interest) | 2017-08-03 | 2017-09-14 | RDS-WHOIS2-RT | 42 | 100% | ICANN org to send drafts
| Define Review Team project management roles and responsibilities, incl, budget management | 2017-08-11 | 2017-10-03 | RDS-WHOIS2-RT | 53 | 100% | Discussed on leadership call #3 (August 11).
| Identify need for and deliver a proposal on division of work | 2017-07-20 | 2017-10-20 | RDS-WHOIS2-RT | 92 | 100% | Subgroups established In Brussels, 3-4 October 2017
| Develop and adopt template for "First pass planning questions" | 2017-10-03 | 2017-10-31 | RDS-WHOIS2-RT | 28 | 100% | Template https://community.icann.org/download/attachments/71604702/First%20Pass%20-%20Planning%20questions%20.docx?version=1&modificationDate=1510149125000&api=v2
| Develop and adopt template for findings and recommendations | 2018-01-02 | 2018-02-09 | RDS-WHOIS2-RT | 38 | 50% | Template https://community.icann.org/download/attachments/71604702/Proposed%20Subgroup%20Report%20Structure%20.docx?version=2&modificationDate=1510149120000&api=v2
| Define structure of subgroups reports | 2018-01-02 | 2018-02-09 | RDS-WHOIS2-RT | 38 | 90% | Template https://community.icann.org/download/attachments/71604702/Proposed%20Subgroup%20Report%20Structure%20.docx?version=2&modificationDate=1510149120000&api=v2
| Define Terms of Reference & Work Plan |  |  |  |  | 62.86%
| Develop methodology to prioritize issues to be addressed in scope, including validating issues against ICANN Bylaws | 2017-07-20 | 2017-09-14 | RDS-WHOIS2-RT | 56 | 100%
| Adopt a framework that identifies the prioritized focus of the work to be performed by the Review Team (Scope) | 2017-07-20 | 2017-10-03 | RDS-WHOIS2-RT | 75 | 100%
| Adopt and publish Terms of Reference | 2017-08-03 | 2018-02-02 | RDS-WHOIS2-RT | 183 | 95% | Submitted to Board Caucus Group for informal feedback
| Adopt and publish Workplan | 2017-09-07 | 2018-02-02 | RDS-WHOIS2-RT | 148 | 95% | Submitted to Board Caucus Group for informal feedback
| Send adopted ToR and Work Plan to ICANN Board | 2017-10-20 | 2018-02-02 | RDS-WHOIS2-RT | 105 | 0% | Submitted to Board Caucus Group for informal feedback
| Provide community with details on adopted terms of reference and workplan | 2018-01-29 | 2018-02-02 | RDS-WHOIS2-RT | 4 | 0% | Blog Posts/Wiki Posts
| Develop and adopt outreach plan | 2017-10-20 | 2018-01-22 | RDS-WHOIS2-RT | 94 | 50% | ICANN org provided a template for Review Team consideration: see https://community.icann.org/pages/viewpage.action?pageId=64084100
| Research and Studies |  |  |  | 240 | 70%
| Assemble repository of background materials | 2016-10-27 | 2018-01-31 | ICANN org | 461 | 100% | Available on dedicated wiki page. ICANN organization to continue populating, as requested
| Identify briefings/data sources needed | 2017-06-05 | 2018-01-31 | RDS-WHOIS2-RT | 240 | 40%
| Determine requirements for independent expert(s) and - if necessary - develop Statement of Work | 2017-10-03 | 2018-01-31 | RDS-WHOIS2-RT | 120 | 70%
| Conduct Review |  |  |  | 233 | 6.292%
Subteams
| WHOIS 1 Review Team Recommendations |  |  |  |  | 7.292%
| Administrative Duties |  |  |  |  | 29.17%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Topic 1 Subgroups | 17 | 95%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Topic 1 Subgroups | 111 | 80% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Topic 1 Subgroups | 111 | 0% | Using template referenced in row 19
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Topic 1 Subgroups | 111 | 0% | Using template referenced in row 19
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Topic 1 Subgroups | 111 | 0% | Using template referenced in row 19
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Topic 1 Subgroups | 80 | 0% | Using template referenced in row 19
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Topic 1 Subgroups | 125 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Topic 1 Subgroups | 111 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Topic 1 Subgroups | 111 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Topic 1 Subgroups | 83 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-02-22 | 2018-03-15 | Topic 1 Subgroups | 21 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-02-22 | 2018-03-15 | Topic 1 Subgroups | 21 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Topic 1 Subgroups | 21 | 0%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Topic 1 Subgroups | 7 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-03-22 | 2018-04-05 | Topic 1 Subgroups | 14 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-04-05 | 2018-04-19 | Topic 1 Subgroups | 14 | 0% | Mid-April: Time identified by leadership for potential face-to-face meeting
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-04-19 | 2018-05-24 | Topic 1 Subgroups | 35 | 0%
| Anything New |  |  |  |  | 3.958%
| Administrative Duties |  |  |  |  | 15.83%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 2 | 17 | 95%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 0% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 0% | Using template referenced in row 14
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 0% | Using template referenced in row 14
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 0% | Using template referenced in row 14
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Subgroup 2 | 80 | 0% | Using template referenced in row 14
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Subgroup 2 | 125 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Subgroup 2 | 111 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Subgroup 2 | 111 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Subgroup 2 | 83 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-02-22 | 2018-03-15 | Subgroup 2 | 21 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-02-22 | 2018-03-15 | Subgroup 2 | 21 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Subgroup 2 | 21 | 0%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Subgroup 2 | 7 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-03-22 | 2018-04-05 | Subgroup 2 | 14 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-04-05 | 2018-04-19 | Subgroup 2 | 14 | 0% | Mid-April: Time identified by leadership for potential face-to-face meeting
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-05-10 | 2018-05-24 | Subgroup 2 | 14 | 0%
| Law Enforcement Needs |  |  |  |  | 3.958%
| Administrative Duties |  |  |  |  | 15.83%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 3 | 17 | 95%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Subgroup 2 | 111 | 0% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Subgroup 3 | 111 | 0% | Using template referenced in row 14
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Subgroup 3 | 111 | 0% | Using template referenced in row 14
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Subgroup 3 | 111 | 0% | Using template referenced in row 14
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Subgroup 3 | 80 | 0% | Using template referenced in row 14
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Subgroup 3 | 125 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Subgroup 3 | 111 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Subgroup 3 | 111 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Subgroup 3 | 83 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-02-22 | 2018-03-15 | Subgroup 3 | 21 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-02-22 | 2018-03-15 | Subgroup 3 | 21 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Subgroup 3 | 21 | 0%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Subgroup 3 | 7 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-03-22 | 2018-04-05 | Subgroup 3 | 14 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-04-05 | 2018-04-19 | Subgroup 3 | 14 | 0% | Mid-April: Time identified by leadership for potential face-to-face meeting
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-05-10 | 2018-05-24 | Subgroup 3 | 14 | 0%
| Consumer Trust |  |  |  |  | 8.125%
| Administrative Duties |  |  |  |  | 32.5%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 4 | 17 | 95%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Subgroup 4 | 111 | 100% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Subgroup 4 | 111 | 0% | Using template referenced in row 14
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Subgroup 4 | 111 | 0% | Using template referenced in row 14
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Subgroup 4 | 111 | 0% | Using template referenced in row 14
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Subgroup 4 | 80 | 0% | Using template referenced in row 14
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Subgroup 4 | 125 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Subgroup 4 | 111 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Subgroup 4 | 111 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Subgroup 4 | 83 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-02-22 | 2018-03-15 | Subgroup 4 | 21 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-02-22 | 2018-03-15 | Subgroup 4 | 21 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Subgroup 4 | 21 | 0%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Subgroup 4 | 7 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-03-22 | 2018-04-05 | Subgroup 4 | 14 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-04-05 | 2018-04-19 | Subgroup 4 | 14 | 0% | Mid-April: Time identified by leadership for potential face-to-face meeting
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-05-10 | 2018-05-24 | Subgroup 4 | 14 | 0%
| Safeguard Registrant Data |  |  |  |  | 8.125%
| Administrative Duties |  |  |  |  | 32.5%
| Confirm members of the Subteam and determine Rapporteur | 2017-10-03 | 2017-10-20 | Subgroup 5 | 17 | 95%
| Establish mandate, objectives and timeline for the work | 2017-10-03 | 2018-01-22 | Subgroup 5 | 111 | 100% | Using template referenced in row 14
| Determine topics for investigation and validate against ICANN Bylaws | 2017-10-03 | 2018-01-22 | Subgroup 5 | 111 | 0% | Using template referenced in row 14
| Identify briefings/data sources needed | 2017-10-03 | 2018-01-22 | Subgroup 5 | 111 | 0% | Using template referenced in row 14
| Determine requirements for independent expert(s) and – if necessary – develop statement of work | 2017-10-03 | 2018-01-22 | Subgroup 5 | 111 | 0% | Using template referenced in row 14
| Adopt statement of work and associated work plan | 2017-11-03 | 2018-01-22 | Subgroup 5 | 80 | 0% | Using template referenced in row 14
| Workplan Execution |  |  |  |  | 0%
| Review, analyze and summarize relevant documentation | 2017-10-20 | 2018-02-22 | Subgroup 5 | 125 | 0%
| Conduct investigation of identified objectives | 2017-11-03 | 2018-02-22 | Subgroup 5 | 111 | 0%
| Conduct relevant interviews as appropriate | 2017-11-03 | 2018-02-22 | Subgroup 5 | 111 | 0%
| Draft summary note of key findings | 2017-12-01 | 2018-02-22 | Subgroup 5 | 83 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2018-02-22 | 2018-03-15 | Subgroup 5 | 21 | 0%
| Assemble draft recommendations using the designated Review Team template | 2018-02-22 | 2018-03-15 | Subgroup 5 | 21 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2018-02-22 | 2018-03-15 | Subgroup 5 | 21 | 0%
| Produce subgroup report for subgroup members' approval | 2018-03-15 | 2018-03-22 | Subgroup 5 | 7 | 0%
| Adopt & Circulate subgroup report to Review Team | 2018-03-22 | 2018-04-05 | Subgroup 5 | 14 | 0%
| Present subgroup report and proposed recommendations to Review Team | 2018-04-05 | 2018-04-19 | Subgroup 5 | 14 | 0% | Mid-April: Time identified by leadership for potential face-to-face meeting
| Refine Draft Report Section |  |  |  |  | 0%
| Incorporate edits suggested by the Review Team, as appropriate | 2018-05-10 | 2018-05-24 | Subgroup 5 | 14 | 0%
Review Team
| Draft Report |  |  |  | 297 | 0%
| Administrative Duties |  |  |  |  | 0%
| Adopt report format | 2018-01-02 | 2018-04-05 | RDS-WHOIS2 Team | 93 | 0% | ICANN org to provide a template
| Internal Review |  |  |  |  | 0%
| Provide input on subgroups' Draft Report sections | 2018-04-05 | 2018-05-10 | RDS-WHOIS2 Team | 35 | 0% | Mid-April: Time identified by leadership for potential face-to-face meeting
| Cross-check draft recommendations with scope and Bylaws | 2018-04-05 | 2018-05-10 | RDS-WHOIS2 Team | 35 | 0% | To be included in FtoF discussions
| Pre-approve draft recommendations | 2018-04-05 | 2018-05-24 | RDS-WHOIS2 Team | 49 | 0% | Organize remote engagement sessions with ICANN SO/AC s, constituency and stakeholder groups / Send a note to SO/ACs, Board Caucus Group, constituency and stakeholder groups to suggest face-to-face update
| Approve draft findings and recommendations | 2018-05-24 | 2018-06-28 | RDS-WHOIS2 Team | 35 | 0%
| Outreach on Draft Recommendations |  |  |  |  | 0%
| Seek community input on draft recommendations | 2018-06-25 | 2018-06-28 | RDS-WHOIS2 Team | 3 | 0% | ICANN 62 (25-28 June 2018)
| Seek input and guidance from the Board Caucus Group and ICANN Subject Matter Experts (SMEs) on implementability of draft recommendations | 2018-06-25 | 2018-06-28 | RDS-WHOIS2 Team | 3 | 0% | ICANN 62 (25-28 June 2018)
| Assembling Draft Report |  |  |  |  | 0%
| Produce Draft Report | 2018-06-28 | 2018-07-13 | RDS-WHOIS2 Team | 15 | 0%
| Publishing Draft Report |  |  |  |  | 0%
| Approve draft report for public comment | 2018-06-28 | 2018-07-20 | RDS-WHOIS2 Team | 22 | 0%
| Send approved draft report sections to language services | 2018-07-20 | 2018-08-17 | ICANN org | 28 | 0% | As sections become available
| Public Comment and Outreach on Draft Report |  |  |  |  | 0%
| Publish draft report for public comment | 2018-08-20 | 2018-10-05 | ICANN org | 46 | 0%
| Seek Board Caucus group and ICANN organization’s input on implementability of draft recommendations | 2018-08-20 | 2018-10-05 | RDS-WHOIS2 Team | 46 | 0%
| Seek Community’s input on implementability of draft recommendations | 2018-06-25 | 2018-10-05 | RDS-WHOIS2 Team | 102 | 0% | Webinars
| Produce summary of public comments | 2018-10-05 | 2018-10-19 | ICANN org | 14 | 0%
| Adopt public comment summary for publication | 2018-10-19 | 2018-10-26 | RDS-WHOIS2 Team | 7 | 0% | ICANN 63 (20-26 October 2018)
| Final Report |  |  |  | 77 | 0%
| Updating Draft Report |  |  |  |  | 0%
| Assemble final recommendations and update draft report based on public comments received | 2018-10-05 | 2018-11-30 | RDS-WHOIS2 Team | 56 | 0% | Including during ICANN63
| Cross-check final recommendations with scope and Bylaws | 2018-10-05 | 2018-11-30 | RDS-WHOIS2 Team | 56 | 0% | Including during ICANN63
| Approval process |  |  |  |  | 0%
| Approve final findings and recommendations | 2018-12-07 | 2018-12-21 | RDS-WHOIS2 Team | 14 | 0%
| Approve final report for submission to ICANN Board | 2018-12-07 | 2018-12-21 | RDS-WHOIS2 Team | 14 | 0%
| Outreach on Draft Final Recommendations |  |  |  |  | 0%
| Provide community with overview of findings and draft final recommendations | 2018-11-30 | 2018-12-21 | RDS-WHOIS2 Team | 21 | 0% | Webinar/blog post
| Send Final Report |  |  |  |  | 0%
| Send final report to ICANN Board | 2018-12-21 | 2018-12-21 | RDS-WHOIS2 Team | 0 | 0%
| Publish final report | 2018-12-21 | 2018-12-21 | ICANN org | 0 | 0%
| Send Final Report to language services | 2018-12-21 | 2018-12-21 | ICANN org | 0 | 0%
| Provide community with overview of findings and final recommendations | 2019-01-07 | 2019-01-11 | RDS-WHOIS2 Team | 4 | 0% | Webinar
| Implementation planning and feedback |  |  |  | 93 | 0%
| Complete ICANN organization survey on review process | 2019-01-08 | 2019-02-08 | RDS-WHOIS2 Team | 31 | 0%
| Identify one or two Review Team Members to remain available for clarification as may be needed during the planning phase of implementation of Review Team Recommendations. | 2018-11-07 | 2018-12-21 | RDS-WHOIS2 Team | 44 | 0%
| Face to Face meetings |  |  |  |  | 25%
| #1 Brussels | 2017-10-02 | 2017-10-03 |  |  | 100%
| #2 F2F Location TBD |  |  |  |  | 0% | Mid-April: Time identified by leadership for potential face-to-face meeting
| #3 ICANN 62 |  |  |  |  | 0%
| #4 ICANN 63 |  |  |  |  | 0%