Subgroup 1: WHOIS1 Rec #1 – Strategic Priority

Work Statement  & Work Plan

| Work Force Identification |  |
| --- | --- |
| Members | - Carlton Samuels - Cathrin Bauer-Bulst - Volker Greimann |
| Rapporteur | Cathrin Bauer-Bulst |
| Scope Objectives | Consistent with ICANN’s mission and Bylaws, Section 4.6(e)(iv), the Review Team will (a) evaluate the extent to which ICANN Org has implemented each prior Directory Service Review recommendation (noting differences if any between recommended and implemented steps), (b) assess to the degree practical the extent to which implementation of each recommendation was effective in addressing the issue identified by the prior RT or generated additional information useful to management and evolution of WHOIS (RDS), and (c) determine if any specific measurable steps should be recommended to enhance results achieved through the prior RT’s recommendations. This includes developing a framework to measure and assess the effectiveness of recommendations, and applying that approach to all areas of WHOIS originally assessed by the prior RT (as applicable). RT1 Recommendations to be assessed by this subgroup: Recommendation #1 - Strategic Priority |
| Comments on Scope, further details | The first WHOIS RT recommended that "WHOIS, in all its aspects, should be a strategic priority, form the basis of staff incentivization (including CEO’s) and organizational objectives; Board should create a committee that includes the CEO to be responsible for priority and key actions; issue public updates on progress against targets for all aspects of WHOIS." |
| Questions we will need to answer in assessing whether the objective has been reached | Has ICANN Org made WHOIS a strategic priority from a formal perspective, by putting into place the appropriate resources and procedures? - How has WHOIS been implemented in staff incentivization including for the CEO? - How has WHOIS been integrated into the organizational objectives? - Has the Board created a committee including the CEO that is responsible for the WHOIS and for key actions? - Has ICANN Org issued public updates on progress against targets for all aspects of WHOIS? - How has the CEO complied with the instruction from the Board to oversee improvements to the contractual conditions relating to gTLD WHOIS data in the gTLD Registry and Registrar agreements? - How has the CEO complied with the instruction from the Board to create appropriate reporting of these improvements and to implement staff incentivisation? Has ICANN Org made WHOIS a strategic priority from a substantive perspective? - Has ICANN taken actions reflecting the strategic priority given to the WHOIS, beyond those specifically recommended by the WHOIS RT? - How was this priority reflected in the transition from the AoC to the Bylaws? - How have WHOIS obligations in contracts improved including in the 2013 Registrar Accreditation Agreement (RAA) and the base new gTLD Registry Agreement? - How have the updated complaints and other compliance procedures impacted the accuracy and functionality of the WHOIS? - Is there evidence to show that the definition as a strategic priority has had a positive impact on the WHOIS in view of the objectives that it serves? |
| Estimate of comparative complexity of assessment (1=low, 5=high) | 2 |
| Estimate of comparative work load (1=low, 5=high) | 2 |
| Estimate of ideal sub-team size (1-5 persons) | 1-2 |
| Work Space URL: | https://community.icann.org/display/WHO/WHOIS1+Rec+%25231+-+Strategic+Priority |
| Mailing List: | rds-whois2-stratpriority@icann.org |
| Important Background Links: | - WHOIS Review Implementation Reports, including - Executive Summary of Implementation Report - Detailed implementation Report - WHOIS Review Team Final Report (2012) - WHOIS1 Implementation Briefings on Recommendations 1, 2, 3, 6, 7, 9, 15, 16 - ICANN Five Year Strategic Plan (p. 12) - https://www.icann.org/en/system/files/files/adopted-opplan-budget-fy17-25jun16-en.pdf (p. 53) (.2 FTE) |

Work Force Timeline

- By 12 December 2017 - Adopt statement of work and associated work plan - By 12 December 2017 - Identify briefings / data sources needed. Determine requirements for independent expert(s) and - if necessary - develop Statement of Work - By 12 January 2018 - Review, analyze and summarize relevant documentation - By 16 January 2018 - Conduct investigation of identified objectives - By 16 January 2018 - Conduct relevant interviews as appropriate - By 16 January 2018 - Draft summary note of key findings - By 30 January 2018 - Approve findings - By 12 February 2018 - Assemble draft recommendations using the designated Review Team template - By 12 February 2018 - Cross-check draft recommendations with scope and Bylaws - By 2 March 2018 - Produce subgroup report for subgroup members' approval - By 9 March 2018 - Adopt & Circulate subgroup report to Review Team - By 16 March 2018 - Present subgroup report and proposed recommendations to Review Team - By 30 March 2018 - Incorporate edits suggested by the Review Team, as appropriate

| Resources |  |
| --- | --- |
| Requests for ICANN briefings | - Briefing on how the WHOIS as a strategic priority has been integrated into the organizational objectives and on the impact that this integration has had in practice, as compared to the approach before 2012 |
| Requests for ICANN materials | - Information on incentivization measures for ICANN Org staff including CEO - Information on Board/CEO Committee on WHOIS including minutes, work plan, objectives and outputs - Any materials that can provide responses to the questions outlined above |
| Interviews to be conducted | To be determined after review of the briefing and materials. |
| Need for Independent Expert | No independent expert is needed. |
| Other resources (existing outside studies, articles) | None |