## Slide 1
ICANN SSr2 review Team
Work summaries – sub-teams
August 7, 2018

## Slide 2: SSR1 Implementation
  Related Bylaw
  4.6 (c)(iv)
  Team Members
  Denise, Alain, Ram Krishna - Rapporteur: Alain
Skillset
  ICANN, SSR1, Audit, Project management
Description of activity
  The sub team will be responsible for reviewing the implementation of the SSR1 RTs work and drafting a document outlining the effectiveness of said implementation
  Complete the assessment of the implementation of SSR1 recommendations, the impact of the implementation, how the post implementation is being managed and what implications for the SSR2 review.

## Slide 3
  Work Items
  Assemble data
  Preliminary review of the implementation of the recommendations
  Elaboration ToR for the consultant (for Implementation’s gap analysis)
  Selection of consultant
  Follow up with consultant to ensure work performed as required
  Review consultant report
  Engage the global review team for consultant report approval
  SSR1 recommendations implementation implications on the SSR2 review

## Slide 4: Achievements
Activity | Date | Status
SSR1 briefings by full review team https://community.icann.org/display/SSR/SSR1+Review+Implementation+Home?preview=/54691765/64084717/SSR1%20Recs%201-28%2031March2017.pdf | March 2017 | 
Sub-groups formation SSR1 Implementation review: Do or hire an independent expert for the Gap analysis on the SSR1 recommendations implementation? | May 2017 | 
SSR1 Review - Meeting #1 Thursday, 20 July 2017 21:00 UTC SSR1 Review - Meeting #2 Thursday, 3 August 2017 21:00 UTC - CANCELLED |  | 
RFP for Gap Analysis of Implementation of SSR1 Review Recommendations published https://www.icann.org/news/announcement-2-2017-09-28-en | September 2017 | 
Only 2 proposals received (16/04/2017) and extension was agreed to November (07/11/2017) | October 2017 | 
Things got paused: Some criticisms from community about hiring an independent expert for the Gap analysis |  | 

## Slide 5: ICANN SSR – Status (Oct, 2017)
Topics/areas for ICANN SSR assessment established
2-day review/interview session with ICANN staff (ICANN LA) Oct 9-10, 2017
Topics covered:
  Stability and Security related to DNS
    Business Continuity Management
    IT operating procedures
    Resource Recovery Plans
    Incident Response
    Root server operations
  Operational Processes of GDD
    Impact on SSR stemming from new gTLDs
    EBERO
    Data Escrow
    CZDS
    SLA Monitoring System
    SADAG/DAAR
  Root Server Management and Operations

## Slide 6: DNS SSR
As per the wiki page for this sub group (https://community.icann.org/display/SSR/Subgroup+%233+-+DNS+SSR) the subgroup's mandate was reviewing ICANNs role in the broader security of the DNS and unique identifiers system, including its role in mitigating threats to the DNS and other unique identities it coordinates.
The first activity of this group was to assemble a set of questions to ask the IANA Manager, Kim Davies, about aspects of the management of Labels entered into the root zone, the NS and DS records and their management, and some questions relating to the DNSSEC signing of the Root Zone. (https://community.icann.org/display/SSR/Subgroup+%233+-+DNS+SSR?preview=/66071179/69276998/2017-08-14-Questions-KD.docx)
The interview occurred with only Geoff Huston and Eric Osterweil on the call (!) Notes from the interview were made, but not posted to the Wiki
Potential issues revealed from the interview were:
  IANA does NOT not regularly monitor NS and DS records in the root zone for data quality and health of the delegation. Previous sensitivities in this area were cited as the reason for this stance.
  IANA does not actively monitor the root zone servers for accurate consistency with the master root zone.
  IANA has no formal operational procedure in the (admittedly unlikely) event of loss of access to the KSK of the root zone.
At this stage the subgroup work stopped due to lack of participation from subgroup members.

## Slide 7: Future challenges - TBC

## Slide 8: IANA Translation - TBC