## Sheet1
Date asked | Asked by | Related Rec # | Question | Answer | Expected delivery date | Date answered | Notes
2017-08-26 | Denise via email | 1 | Since the version developed in 2012, what changes have been made to the SSR remit and technical mission statement? Who has made those changes? How has the community been allowed to review and comment on those changes? When were the last changes made to this statement? | Answers to this question available here (published in in 2015): https://www.icann.org/resources/pages/ssr-role-remit-2015-01-19-en |  | 2018-09-24
2017-08-26 | Denise via email | 1 | How are the definitions of security, stability and resiliency consistently carried through into key documents, such as strategic plans and agreements with contracted parties? | Because of the variety of subjects that this question incorporates, it is difficult to address. Different departments work on different aspects of this question and don’t always have visibility to the topics covered in the question. Because of this, ICANN ORG operates in a “Best Effort” model and reaches out to OCTO-SSR if any questions arise surrounding the use of the definitions. To date, ICANN ORG feels that it has stayed consistent with the usage of the definitions between the various types of documents. |  | 2018-09-27
2017-08-26 | Denise via email | 2 | Recommendation 2 directs that the definition of ICANN’s SSR remit and limited technical mission should be reviewed in order to maintain consensus and elicit feedback from the Community. Please provide details of reviews and community feedback that have occurred since 2013.
2017-08-26 | Denise via email | 2 | As ICANN’s SSR remit and limited technical mission statement has evolved, how has comment from the community been incorporated? For instance, is there a summary of the comments on the FY 2014 Framework? Where is this published?
2017-08-26 | Denise via email | 3 | In what way has ICANN publicized consistent terminology and descriptions related to ICANN’s SSR role and remit? Where are these published? | Document of definitions is available here: https://community.icann.org/pages/viewpage.action?pageId=64074062&preview=/64074062/64076676/SSR%20Def_Steve%20Conte.pdf |  | 2017-03-15 | Answered at face-to-face meeting #1, 15 March 2017. Meeting trascript available here: https://community.icann.org/x/TrHRAw
2017-08-26 | Denise via email | 3 | What terms related to SSR have been added to the ICANN public glossary? When were they added? | See here: https://www.icann.org/icann-acronyms-and-terms/en/G0301
2017-08-26 | Denise via email | 4 | What accounts for the inconsistencies between the different documents on the ICANN website that describe the nature of the SSR relationships it has within the ICANN community?
2017-08-26 | Denise via email | 4 | In what way are these documents fulfilling the requirement to provide a single focal point for understanding the interdependencies between organizations? | MOUs are in place that have been incorporated as part of the agreements. We have several links in place for ICANN security resource locator development, and a document published in January of 2017, that identifies, in detail, all the relationships. This information can be found here: * ICANN’s major agreements and related reports are published at: https://www.icann.org/en/about/agreements * Detailed breakdown of ICANN’s SSR Relationships is located at: https://www.icann.org/en/system/files/files/ssr-relationships-fy17-23jan17-en.pdf * ICANN’s Security Awareness Resource Locator page can be found at: https://www.icann.org/resources/pages/security-awareness-resource-2014-12-04-en |  | 2017-05-14 | Plenary meeting 11 Madrid day 1 page 125 of meeting transcript posted here: https://community.icann.org/x/LxTfAw
2017-08-26 | Denise via email | 4 | What opportunities have there been for community input into the nature/definition of ICANN’s SSR relationships? | This document is revisited and revised periodically with new versions being publlished as such. The community is always able to provide input given ICANN's commitment to transparency but there is no official public comment process on the relationships. |  | 2018-09-24
2017-08-26 | Denise via email | 4 | How is the document describing SSR relationships with partner organizations being updated? | This document was prepared in accordance with recommendation 4. There is no established process in place for updating it. |  | 2018-09-27
2017-08-26 | Denise via email | 6 | What is the status of the document currently available at: https://www.icann.org/en/system/files/files/draft-rssac-ssac-roles-responsibilities-05mar15-en.pdf? |  | 2018-09-28
2017-08-26 | Denise via email | 6 | The recommendation requires that ICANN should seek consensus for this document across both groups. Please provide documentation that this occurred. |  | 2018-09-28
2017-08-26 | Denise via email | 6 | What specific resourcing for RSSAC and SSAC appears in either the ICANN Operating Plan or the most recent budget? |  | 2018-09-28
2017-08-26 | Denise via email | 7 | How are the objectives specific to the SSR Framework documented in either the Operating Plan or the Strategic Plan? | The components of the SSR Framework are included in the ICANN strategic plan. SSR related KPI’s in the strategic plan are related FY2016 –2020 Strategic Objective 2: Support a healthy, stable, and resilient unique identifier ecosystem: 2.1) Foster and coordinate a healthy, secure, stable, and resilient identifier ecosystem. 2.2) Proactively plan for changes in the use of unique identifiers and develop technology roadmaps to help guide ICANN activities. 2.3) Support the evolution of domain name marketplace to be robust, stable and trusted. Progress against these KPIs is available here: https://www.icann.org/accountability-indicators |  | 2017-05-14 | Plenary meeting 11 Madrid day 1 page 119 of meeting transcript posted here: https://community.icann.org/x/LxTfAw
2017-08-26 | Denise via email | 7 | Where are priorities for SSR activities and initiatives published? | We have identified SSR related KPI’s in the strategic plan. ICANN's strategic plan is here: https://www.icann.org/en/system/files/files/strategic-plan-2016-2020-10oct14-en.pdf. More details are available here: https://www.icann.org/resources/pages/strategic-engagement-2013-10-10-en |  | 2017-05-14 | Plenary meeting 11 Madrid day 1 page 119 of meeting transcript posted here: https://community.icann.org/x/LxTfAw
2017-08-26 | Denise via email | 7 | In what ways have pragmatic cost-benefit and risk analysis informed the choice of priorities (if any)? | Over the last couple of years, risk & opportunity and financial assessments have been progressively entrenched to inform and drive prioritization. The FY18 Strategic Trend Outlook assessment was conducted with every functional team within org, the Board and community. The assessment results inform the annual operating plan update and budget and form the foundation for the next Five-Year Strategic Plan. Financial (cost/benefit) assessments have been a key focus within org, the Board and community in developing annual budgets and driving numerous cost-saving initiatives. | 2018-09-28 | 2018-09-25
2017-08-26 | Denise via email | 7 | In addition to the ability to comment on draft ICANN budgets and plans, how is the community able to provide input into the objectives, initiatives and activities related to SSR at ICANN? | As ICANN publishes its SSR frameworks, they are open to community review and comment. In light of the changes that took place during the IANA transition a new SSR Framework is currently in the making and will be published for review. |  | 2018-09-24
2017-08-26 | Denise via email | 7 | The SSR1 Report indicates that ICANN will “improve and publish a process for establishing updated SSR priorities and objectives.” Where has this been published? Was there a mechanism for community review of the process (if so, please provide links)?
2017-08-26 | Denise via email | 9 | SysTrust certification is referenced in the SSR1 Report as already in place. Please explain how it is claimed to be implementation of SSR1. | Certification options were assessed after the SSR1 final report was published. Within the IANA Function’s team, two different audits are completed on an annual basis. SOC3 Certification of Root Zone KSK System, and SOC2 Certification for our Registry Assignment and Maintenance Systems. These audits evaluate our service organization controls (SOCs) against the “Trust Services Principles and Criteria”. This is a well-established framework that’s certified by the American Institute of Certified Public Accountants and the Canadian Institute of Chartered Accountants for assessing organization controls over security systems. More information is available here: https://www.iana.org/about/audits |  | 2017-06-25 | Plenary meeting 17 Johannesburg day 1. Meeting transcript posted here: https://community.icann.org/x/Bw7fAw
2017-08-26 | Denise via email | 9 | Beside the certifications/audits done for processes in IANA, what certification activities have been assessed or implemented related to SSR? |  | 2018-10-04
2017-08-26 | Denise via email | 9 | For staff working on SSR-related objectives, is there a certification plan in place as part of career/staff development? |  | 2018-10-04
2017-08-26 | Denise via email | 9 | When was the EFQM model implemented within ICANN, and please provide details of how the SSR Framework and standard operating procedures have been evaluated and updated in the light of EFQM adoption to demonstrate process improvements over time. | ICANN IANA functions have implemented the EFQM since 2009, and ICANN has also been implementing the EFQM model org-wide since FY15. The SSR Framework and standard operating procedures have been part of the process improvement assessment focus along with the model adoption. | 2018-09-28 | 2018-09-25
2017-08-26 | Denise via email | 9 | Has ICANN ever published a document that would include “a clear roadmap towards certification?” If so, where? Was there a mechanism by which community comment or engagement took place for such a document? |  |  | 2017-06-25 | Plenary meeting 17 Johannesburg day 1 page 107-112 of meeting transcript posted here: https://community.icann.org/x/Bw7fAw
2017-08-26 | Denise via email | 10 | Please provide a summary of the number of complaints and enforcement actions against registries and registrars taken by contractual compliance on the basis of SSR obligations in the past 5 years. | ICANN has a dedicated public page for Contractual Compliance Reporting. This page provides three types of data to the ICANN Community. The first section, referred to as Metrics and Dashboards, provides monthly, quarterly and annual data. The second section, referred to as Contractual Compliance Metrics for a rolling 13-month period, provides ten different types of reports for a period of 13-month. The third section, referred to as Additional Contractual Compliance related data, provides links to the metrics and data specifically requested by different working groups or review teams. A summary of the number of complaints and enforcement actions against registries and registrars, including the number of complaints by complaint type can be found at https://features.icann.org/compliance/dashboard/report-list. As for enforcement, there are multiple reports to refer to: a) In the Metrics and Dashboards section, there are two reports to provide enforcement data; a report that presents data about the Formal Resolution Process broken out by enforcement reason (https://features.icann.org/compliance/dashboard/2018/q2/enforcement-complaint-type) and another that shows the data from a Compliance Approach & Process (https://features.icann.org/compliance/dashboard/2018/q2/complaints-approach-process-registrars) perspective for registrar and another for registry related complaints. Same reports can also be found in the Annual Report section. b) in the 13-month rolling section, there is a Formal Notices (https://features.icann.org/compliance/enforcement-notices) report that lists enforcement actions by a contracted party and the enforcement reasons for both registrars and registries | 2018-10-01 | 2018-09-25
2017-08-26 | Denise via email | 10 | To what extent does ICANN measure the incidence and impact of registration abuse and/or malicious conduct by contracted parties? | ICANN Contractual Compliance reports on the total number of registrar abuse report complaints received and processed. In late 2017, compliance reporting included the subject matter category in its monthly metrics; for example - the abuse complaint type now provides the subject of registrar related Domain Name System (DNS) abuse complaints such as spam, pharming, phishing, malware, and botnets in addition to counterfeiting, pharmaceutical, fraudulent and deceptive practices, trademark or copyright infringement, and registrar abuse contact. ICANN Contractual Compliance also proactively monitors compliance with the abuse-related obligations of the Registrar Accreditation Agreement and Registry Agreement through audits. At the closure of every audit round, ICANN published an audit report on the Reports & Blogs Page (https://www.icann.org/resources/compliance-reporting-performance). ICANN org is developing use of the information from the Domain Abuse Activity Reporting (DAAR) (https://www.icann.org/octo-ssr/daar) project for studying and reporting on domain name registration and security threat (domain abuse) behavior across registrars and registry operators. | 2018-10-01 | 2018-09-25
2017-08-26 | Denise via email | 11 | What measurements exist, and are used, for the effectiveness of mechanisms to mitigate domain name abuse, as required in recommendation 11?
2017-08-26 | Denise via email | 11 | Please provide details of the measures of success relating to new gTLDs and IDNs that expressly address SSR related program objectives. The link in the SSR1 Report (https://community.icann.org/display/SSR/Rec+%2311 ) did not resolve. | The implementation report for recommendation 11 can be found here: https://community.icann.org/display/SSR/Rec+%2311?preview=/56140534/64082817/SSR%20RT1%20Recommendation%2011%20Implementation%20Report-%20Final.pdf |  | 2018-09-24
2017-08-26 | Denise via email | 11 | Please provide details of how SSR objectives are explicitly referenced in ICANN’s standard operating procedures, Service Level Agreements and monitoring, emergency back- end registry operators and data escrow, Trademark Clearinghouse, root zone scaling management, DNSSEC-related activities, and Compliance Dept. activities.
2017-08-26 | Denise via email | 11 | Noting IAG-CCT produced 70 metrics of which a single one (1.13) related to security issues; please provide details of the information gathered according to that metric. The web page of metrics and measures does not include information relating to 1.13.
2017-08-26 | Denise via email | 11 | The SSR1 Report refers to Specification 11 as applying to all new gTLD registries. Please provide reports on the number and type of security threats reported by registries under their Specification 11 obligations. Please give details of enforcement action(s) taken by ICANN’s contractual compliance department in relation to Specification 11. | Details regarding ICANN Contractual Compliance’s enforcement of registry operator security threat reporting obligations under Specification 11 have previously been published in response to requests for similar information from the new gTLD Subsequent Procedures Policy Development Process Working Group at https://community.icann.org/download/attachments/58735937/New%20gTLD%20Subsequent%20Procedures%20Request%20for%20Data%20%28PIC%29.docx?version=1&modificationDate=1502819042000&api=v2. To date, ICANN has issued two breach notices related to Specification 11. Both were on the basis of noncompliance with Section 3(c), regarding transparent operation of the subject top-level domain. Details regarding these notices are published at https://www.icann.org/uploads/compliance_notice/attachment/911/serad-to-westerdal-16mar17.pdf and https://www.icann.org/uploads/compliance_notice/attachment/1049/serad-to-allain-11jul18.pdf . No enforcement actions have been issued to date on the basis of Specification 11 3(b), regarding security threat reporting. Additionally, ICANN Contractual Compliance has recently conducted a registry audit which focused on registry operator compliance with Specification 11 security threat reporting obligations. An audit report regarding this audit round is estimated to be published by the end of October 2018 at the audit reports page, which can be linked to from https://www.icann.org/resources/pages/audits-2012-02-25-en. | 2018-10-01 | 2018-09-25
2017-08-26 | Denise via email | 11 | How many new gTLD applications were failed (or placed in contention or required to take additional steps) on the basis of the (i) the security and stability review or (ii) the string similarity review. |  |  |  | Clarification requested via email 14 September 2018
2017-08-26 | Denise via email | 11 | In relation to the IDN ccTLD Fast Track, please give details of any strings that have failed those security and stability checks for security and stability related reasons rather than for consumer confusion – a CCT Review issue.
2017-08-26 | Denise via email | 11 | Considering staff and community feedback, how effective is the EPSRP mechanism (the second security and stability review in the IDN ccTLD Fast Track) in detecting and preventing stability and security issues other than consumer confusion?
2017-08-26 | Denise via email | 11 | Are there any updates on the status of Coordinated Vulnerability Disclosure Reporting since 2013? | This link contains the latest information that has been published.: https://www.icann.org/news/blog/icann-coordinated-disclosure-guidelines |  | 2018-09-24
2017-08-26 | Denise via email | 11 | Please provide a copy of the report referred to in bullet point 9 of recommendation 11 implementation in the Final Implementation Report. Given that the SSR objectives referred to in the report remain ‘to be defined’ please provide an explanation as to why this recommendation is said to be complete. | The link to the report is here: https://community.icann.org/display/SSR/Rec+%2311?preview=/56140534/64082817/SSR%20RT1%20Recommendation%2011%20Implementation%20Report-%20Final.pdf. The work was deferred to the SSR2 Review Team as stated in the report. As such, this recommendation was marked as complete because the work could not progress any further without the SSR2 Review Team taking this on. | 2018-09-30 | 2018-09-24
2017-08-26 | Denise via email | 11 | To what extent was the commissioning of the CDAR report, the Root Stability Study Workshop and the new gTLD program security and stability impact triggered by the SSR1 recommendation, and why is the SSR1 Report not referenced in the published materials relating to those initiatives? |  | 2018-09-27
2017-08-01 | Denise during briefing | 11 | What was happening in the 5 years between when the recommendation was approved by the Board and when a draft consultant report was posted in April 2017? | We cannot speak for the first few years after the recommendation was approved by the Board because the staff working on the recommendation are no longer at ICANN org. At the point from when we do have a record of when the work was started, a consultant with the appropriate expertise was brought on board to implement the recommendation. Due to unforeseen personal circumstances of the consultant, work on this implementation was delayed. The consultant was able to finish the work prior to April 2017, at which the report was posted. | 2018-09-30 | 2018-09-24
2017-08-01 | Denise during briefing | 11 | On the status and deliverables of Rec 11 it says that ICANN has implemented measures of success for the gTLDs, but we haven’t seen how you’ve implemented measures of success for new gTLDs and IDNs. That’s the first check mark, but what we’ve been provided with is a draft report of some ideas that you could do. How is that considered full implementation of this recommendation? | An independent consultant was hired to implement this recommendation. The consultant’s report states, “The measures of success anticipated by the SSR RT in Recommendation 11 assume the existence of a community-based definition of “success” with corresponding metrics that could serve as the basis for measurement. These do not exist for the new gTLD program nor the IDN ccTLD Fast Track program. This report recommends that success criteria and measurements that have been developed for closely related ICANN activities—particularly the Competition, Consumer Choice, and Consumer Trust Review Team (CCCT RT)—be considered responsive to Recommendation 11, and that the issue of appropriate SSR metrics specific to the new gTLD program and the IDN ccTLD Fast Track be revisited by the second Security, Stability & Resiliency of the DNS Review Team (SSR RT2).” The report can be found here: https://community.icann.org/display/SSR/Rec+%2311?preview=/56140534/64082817/SSR%20RT1%20Recommendation%2011%20Implementation%20Report-%20Final.pdf | 2018-09-30 | 2018-09-26
2017-08-01 | Denise during briefing | 11 | The SSR1 review team called out a number of activities that were operational and within staff’s purview and contained in the SSR framework and called for implementation of measurements and metrics. Was that work done and is it captured anywhere? To clarify, as part of the SSR1 report related to rec 11, the SSR1 review team noted ICANN administration of the new gTLD Program, IDN program, significant SSR related issues that are in the framework. They called for more specific goals, measurements and impact assessment. Was that work done and is it captured somewhere else? |  | 2018-09-30
2017-08-01 | Denise during briefing | 11 | Within the area of recommendation 11 & 12 activities for which ICANN can be a facilitator or convener – is there more information on the steps that ICANN took over the past five years to facilitate activites that involve other entities that had primary ownership or responsibility on related activities?
2017-08-01 | Denise during briefing | 11 | In looking at the dashboard for rec 11 and all the checkmarks including operational items, it’s really unclear how staff defined and measured success related to SSR. It’s hard to see how the basic spirit of this recommendation was implementation, especially with an idea paper from a consultant. But in terms of the last 5 years and what staff did to implement, it’s unclear. Can you gather more information and provide more clarity and facts? | As noted in the answers to previous questions, the report from the consultant indicated that the measures of the success need to be defined by the community since they do not exist. Due to unforeseen personal circumstances of the consultant, work on this implementation was delayed. The consultant was able to finish the work prior to April 2017, at which the report was posted. | 2018-09-30 | 2018-09-28
2017-08-01 | Geoff during briefing | 11 | In a commercialized world of DNS service provision where data is considered to be a corporate asset, do you feel that either ICANN or the community at large have access to meaningful metrics? I cite the barriers that exist on information on root servers. Is this a barrier to the entire objective, that access to data appears to be challenging? | Geoff Huston (asker) clarified that he feels this is a question for the review team to answer, not ICANN org.
2017-08-01 | Geoff during briefing | 11 | Do you think it is ICANN staff’s responsibility to gather, analyze and publish this data or do you feel that it’s ICANN’s responsibility to facilitate others to do that? | ICANN as an organization looks to community to define what success is especially in a program like that like the New gTLD Program and the IDN Fast Track program from the ccNSO. I don’t believe ICANN imposes measures of success on those groups. And I think it’s a community effort in which we look for guidance from the community on what those measures are. And then depending on what the result is, it would determine whether or not ICANN is the implementer of those measures of success or the shepherd of those measures. One of the challenges that we faced specifically around this recommendation and around those programs was that we didn’t have any community definition of success or those measures, so we couldn’t have any baseline in which to conduct measurements off those. |  |  | Answered during breifing. Transcript available here: https://community.icann.org/x/jXHwAw
2017-08-01 | Denise during briefing | 11 | Which sections of the revised new gTLD registry agreement does OCTO staff feel advance SSR best practices and objectives?
2017-08-26 | Denise via email | 12 | In what way have the recommendations contained in the paper, “Identifier System Attack Mitigation Methodology,” been integrated into contracts, agreements and MoUs as envisioned by SSR1 recommendation 12?
2017-08-26 | Denise via email | 12 | Is there a central, up-to-date resource to see how the ISSSR team, and other professionals in the SSR field, have worked with SOs and ACs to identify additional, targeted best-practices for their constituents? Are there pointers to or records of those engagements? | Interactions with SOs and ACs are documented through the regular ICANN processes. SSR interactions are not specifically flagged in any way beyond meetings at ICANN being labelled as of interest for those in the community with a security interest. One such effort could be OCTO SSR team member participation in the ccNSO TLD-OPS discussions list (a small subset of ccNSO) but these are not documented by OCTO SSR. More information about the ccNSO TLD-OPS can be found here: https://ccnso.icann.org/en/resources/tld-ops-secure-communication.htm |  | 2018-09-26
2017-08-26 | Denise via email | 12 | What are some examples of significant MoUs with international entities that have SSR-practices embedded within them?
2017-08-26 | Denise via email | 12 | Is the only place where ICANN has documented work on recommendations for web application protection and development of resources for security awareness in the report from the 4th Global DNS Stability, Security and Resiliency Symposium? | Yes |  | 2018-09-24
2017-08-26 | Denise via email | 12 | Has there been a Global DNS Stability, Security and Resiliency Symposium since 2014? | No there has not. There have been other symposia such as IDS. |  | 2018-09-24
2017-08-01 | Denise during briefing | 12 | With regards to establishing best practices and integrating these into agreements to which ICANN enters: The SSR1 report is linked to a paper that raises a whole host of issues and addresses proposed activities but it’s unclear how that then relates to integrating those into agreements into which ICANN has entered over the past 5 years. Can you provide more specific information on how best practices are reflected in agreements that ICANN has entered into?
2017-08-01 | Denise during briefing | 12 | ‘Addressing SSR practices in MOUs’ links to a page that holds all of the MOUs. Can you provide some quantification of SSR-related practices in MOUs and more information on which ones contain SSR-related practices, which practices they contain, and how all that’s tracked or the implementation is assessed?
2017-08-01 | Matogoro during briefing | 12 | What has changed after the implementation of Rec#12 as compared with the past? | Recommendation 12 has driven ICANN’s SSR Team - now ICANN's OCTO SSR Team - to continue to build their engagement both on an individual networking level, and to engage heavily with ICANN’s GSE Department (Global Stakeholder Engagement). The OCTO Team has worked with GSE since this recommendation. ICANN’s OCTO Team works closely with Global Stakeholder Engagement Team in order to help facilitate and clarify some of the needs of the GSE regional strategies as they’re being built. More visibility to the strategies in draft form helps OCTO to make sure we have the right resources and budget in order to support the activities that ICANN's regional VPs want to facilitate within the region. Earlier visibility to the regional strategies gives us a chance to be more responsive and proactive on the ground in supporting the GSE Team in the regions. Although OCTO SSR is completely request-driven, we used to be completely ad hoc request-driven, which means that a request would come in, we would go and satisfy that. This was cost-prohibitive and inefficient. Now we are more deliberate in our actions, especially traveling and being physically in the region. We work with the GSEs prior to any travel to try to utilize team members time with meetings and presentations that are relevant during their travel to maximize efficiency. So, we set up meetings with key delegates in the region or we might be doing a training on DNSSEC but at the same time, while we’re out in that region, we might also meet with local law enforcement or the regional Interpol, for example. |  | 2017-08-01 | Answered during meeting. Transcript available here: https://community.icann.org/x/jXHwAw
2017-08-26 | Denise via email | 13 | In what way are the resources on the ICANN Security Awareness Resource Locator supposed to help Supporting Organizations secure collaborative community assets? |  | 2018-09-28
2017-08-26 | Denise via email | 13 | Have any recent steps been taken to encourage SOs and ACs to produce and publish best practices repositories for SSR-related information? Is the 2012 information on the ccTLD website the most recent example of SSR-related information published by a Supporting Organization? |  | 2018-09-28
2017-08-26 | Denise via email | 14 | When is the Annual Report for FY 2016-2017 going to be published as a community resource? |  | 2018-10-03
2017-08-26 | Denise via email | 14 | In the ICANN Engagement Interface, are all the SSR-Related outreach activities recorded or listed? | Yes, Global Stakeholder Engagement does have a tool where we capture our engagement events, called ICANN CRM. We are working to streamline the ICANN CRM in FY19-FY20 so that it captures all of the SSR-related outreach activities. Starting with FY19, Global Stakeholder Engagement will be reporting on its work across five areas: • Capacity Development (which includes technical training and related engagement in the regions to support stakeholders become active participants in ICANN’s technical and policy work) • GSE Administration (This project covers administrative functions for the Global Stakeholder Engagement team, such as management of department budget, personnel, visas, allocation of resources.) • Engagement Measurement and Planning (Project coordinates GSE Engagement, Measurement & Planning function, maintaining team goals and measurement of engagement. Management of GSE processes and procedures, inputs into ICANN CRM.) • Cross-Organizational Collaboration (This project covers cross-regional and functional coordination activities for GSE with other ICANN Org departments (contributions to ICANN Strategic & Operational Planning, Community Engagement & Policy, event tracking, GDD-GSE engagement collaboration, support for Policy implementation, inputs to Enterprise Risk Management, inter-departmental collaboration). Travel and logistics for participation in ICANN Org workshops, regional meetings). • Facilitation of Regional Participation in ICANN (This project covers Global Stakeholder Engagement work for enhancing cooperation and partnerships regionally to lower barriers to participation among stakeholder groups, and increase regional engagement within ICANN in its technical & policy work. This project includes the regional engagement plans and strategies, facilitation of regional events such as ICANN Readouts, regional DNS Forums, regional event sponsorships, contributions and collaborations). |  | 2018-09-27
2017-08-26 | Denise via email | 15 | Is there any record of the methodology in the Coordinated Vulnerability Disclosure Document ever being invoked since 2013? |  | 2018-10-04 | 2017-05-14
2017-08-26 | Denise via email | 15 | Are there any statistics available for the processes identified in the Coordinated Vulnerability Disclosure Document? |  | 2018-10-04
2017-08-26 | Denise via email | 15 | Are there any metrics or statistics available for ICANN’s engagement with operators and trusted community entities on DNS security threats and mitigation techniques? | Such events are normally kept confidential unless the effected parties wish to discuss them openly. We do not have statistics. |  | 2018-09-24
2017-08-26 | Denise via email | 16 | What public engagement was done for the creation of the Frameworks and Annual Reports? | Outreach activities and processes solicit input on the SSR Framework have been expanded and are part of ICANN’s SSR SOP; activities are ongoing and are reviewed annually. For example: the Security team’s ongoing work with security communities including the Anti Phishing Working (APWG), the Messaging, Malware and the Mobile Anti-Abuse Working Group (MAAWG) has resulted in participation by members of those communities in SSAC; through engagement with the International Criminal Law Network (ICLN) and Commonwealth Cybercrime Initiative (CCI), the Security team emphasizes the value of multistakeholder approaches to cybersecurity issues. Information is available here: https://www.icann.org/news/blog/identifier-systems-ssr-activities-reporting-en |  | 2017-05-14 | Plenary meeting 11 Madrid day 1. https://community.icann.org/pages/viewpage.action?pageId=64951343&preview=/64951343/66091524/ssr2-14may17-en.pdf
2017-08-26 | Denise via email | 16 | Is there a record showing how Community participation and input into the SSR Framework was incorporated? | Whenever a new framework is drafted it goes out for comment, which has it's own ICANN processes. |  | 2018-09-27
2017-08-26 | Denise via email | 16 | Are the documents that used to be called Frameworks, now to be SSR Annual Reports? If so, what is the community engagement mechanism being used for the Annual Reports? | No. They are called Frameworks but had been named incorrectly on the SSR document archive. This page https://www.icann.org/ssr-document-archive has been updated with this correction. |  | 2018-09-13
2017-08-26 | Denise via email | 16 | The implementation report specifically mentions capability building initiatives that would affect greater engagement in the development of the SSR Frameworks or Annual Reports. What initiatives have taken place? Who has participated? How have they expanded participation and input into the SSR Framework development process? |  | 2018-10-05
2017-08-26 | Denise via email | 17 | What is an example of a more structured internal process for showing how activities and initiatives relate to specific strategic goals, objectives and priorities in the SSR Framework? Has this been incorporated into the internal “At Task” system or other internal management systems? | All goals are incorporated into our internal systems that track activities to the strategic priorities. At-task is one of these systems. |  | 2018-09-27
2017-08-26 | Denise via email | 17 | Are there any statistics available for the processes identified in the Coordinated Vulnerability Disclosure Document? |  | 2018-10-04
2017-08-26 | Denise via email | 17 | Are there any metrics or statistics available for ICANN’s engagement with operators and trusted community entities on DNS security threats and mitigation techniques? | Such events are normally kept confidential unless the effected parties wish to discuss them openly. I do not believe we have statistics. |  | 2018-09-24
2017-08-26 | Denise via email | 19 | In ICANN’s Portfolio Management system, the only SSR-related activity that appears is KSK Rollover. Is there another place where SSR-activities are tracked so that the community can see progress on current year activities (for instance the KPI Dashboard seems to be entirely related to the OCTO’s work with the technical and public safety communities)?
2017-08-26 | Denise via email | 20 | Provide documentation of, and links to, mechanisms that have been used since 2012 to provide more detailed public information on SSR-related budgets and expenditures across multiple ICANN departments | Recommendation 20 was implemented in March – April 2017. The public information on SSR-related budget and expenditures across multiple ICANN departments was posted for FY18 and can be found here: https://community.icann.org/x/CqNYAw | 2018-09-30 | 2018-09-26
2017-08-26 | Denise via email | 20 | Have any after-event reports (for relevant threats) been published that include budget and resource impacts related to managing the event? What would be an example of this kind of after-event-report? |  | 2018-10-04
2017-10-09 | Denise via email | 21 | Is there a link to the template described in the staff implementation report? | Since the template has now been put to use, the actual report for FY18 has replaced the template and it can be found here: https://community.icann.org/x/DKNYAw | 2018-09-30 | 2018-09-26
2017-10-09 | Denise via email | 21 | Is there a plan for getting public comment on the template prior to using it for publishing information on budget and resource impacts related to SSR events? | No. There was no plan in place to ask for public comment on the template. The FY18 report has been published and it can be found here: https://community.icann.org/x/DKNYAw | 2018-09-30 | 2018-09-26
2017-10-09 | Denise via email | 21 | Where is the budgetary information as it pertains to the SSR? And where is the cost benefit analysis for making these decisions? | The budgetary information relative to SSR can be found mainly under Objectives 2 and 3 in the Operating Plan and in the Budget by portfolio. As an example, see links to the F19 documents: FY19 Operating Plan: https://www.icann.org/en/system/files/files/adopted-opplan-fy19-30may18-en.pdf FY19 Adopted Budget by Portfolio & Project: https://www.icann.org/resources/files/1215649-2018-05-18-en |  | 2018-09-19 | Clarification required for the second part of the question, "And where is the cost benefit analysis for making these decisions?"
2017-10-09 | Denise via email | 21 | Where is the evidence that a more structured internal process has been developed for SSR budgetary considerations? How do these decisions map onto ICANN’s planning framework and process? | ICANN’s planning process ensures that activities planned and budgeted for, including those related to SSR, are identified by specific objectives. More information about the planning process is available here: https://www.icann.org/resources/pages/governance/planning-en |  | 2018-09-19
2017-10-09 | Denise via email | 21 | Can ICANN provide an update as to the status of phase two (identifying mechanisms that that provide detailed public information on SSR-related budgets), and the steps still to be taken to ensure this recommendation is properly implemented? | Recommendation 20 was implemented in March – April 2017. The public information on SSR-related budget and expenditures across multiple ICANN departments was posted for FY18 and can be found here: https://community.icann.org/x/DKNYAw | 2018-09-30 | 2018-09-26
2017-10-09 | Denise via email | 22 | Recommendation 22 is specifically about the new gTLD program. What documentation, specific to the new gTLD Program, on the organization, budget and resources needed to manage SSR issues in this area is available? | The public information on SSR-related budget and expenditures across multiple ICANN departments was posted for FY18 and can be found here: https://community.icann.org/x/DqNYAw . This report is updated annually and covers direct costs resulting from the activities required to perform the SSR Functions, direct costs of shared resource and the costs of support functions allocated to SSR. | 2018-09-30 | 2018-09-26
2017-10-09 | Denise via email | 22 | Since the publication of the SSR1 report, what materials have been published by the SSR team that are specific to the implementation of the new gTLD Program? How has that work been budgeted and resourced? | The OCTO SSR team does not have projects specific to the new gTLD program. These would fall mainly under GDD, which the OCTO SSR team may support. |  | 2018-09-24
2017-10-09 | Denise via email | 23 | Recommendation 23 calls for a mechanism for Working Groups and Advisory Councils to support their decisions in an objective manner that is free from external or internal pressure. Where is such a mechanism documented – specifically regarding the work of SSAC and RSSAC? |  | 2018-09-28
2017-10-09 | Denise via email | 25 | Since the publication of the SSR1 Final Report, what mechanisms have been put into place to incorporate near and long-term risks into a formal, strategic Risk Management Framework for ICANN? | ICANN org has established a revised risk management framework. This includes thus far establishing an org Risk Management Committee of the org execs, gaining approval for the org’s first risk management policy, establishing a Function Risk Liaison Network in which each function is represented in a cross-functional team, and refreshed the risk register, which would be including risks into a formal framework. This framework is moving towards the most important elements of the Risk Management target operating model. |  | 2018-09-28
2017-10-09 | Denise via email | 25 | Since the Board approval of the 2014 Risk Management Framework provided by an external consultant, what further review, consultation or further work has been done on the approved Framework? | ICANN org has established a revised risk management framework. This includes thus far establishing an org Risk Management Committee of the org execs, gaining approval for the org’s first risk management policy, establishing a Function Risk Liaison Network in which each function is represented in a cross-functional team, and refreshed the risk register, which would be including risks into a formal framework. This framework is moving towards the most important elements of the Risk Management target operating model. |  | 2018-09-28
2017-10-09 | Denise via email | 25 | Please provide evidence of briefings to the Board Risk Committee on the risk assessment and proposed mitigation measures, as per Board Resolution dated 21 November 2013 https://features.icann.org/dns-risk-management-framework-report-and-implementation?language=fr, and any follow up arising from such briefings. | There is no operational “DNS Risk Management Framework.” ICANN org now has a risk management framework which covers all risks faced by ICANN org, not just the DNS. Regarding briefings to the BRC about the risk management framework, the BRC meetings have publicly available minutes. Minutes are published to this page: https://www.icann.org/resources/pages/minutes-2014-03-24-en |  | 2018-09-28
2017-10-09 | Denise via email | 25 | What efforts have been made since 2014 to demonstrate that ICANNs risk management framework follows the standards of transparency and community participation, required by the SSR1? | We have not yet developed mechanisms to communicate more broadly on risk management. ICANN risk management will work with ICANN managements and the BRC on next steps. |  | 2018-09-28
2017-10-09 | Denise via email | 25 | Please clarify whether the portfolio of the new VP of Enterprise Risk Management extends into risks relating to ICANN's role with regard to the internet's set of unique identifiers, and future threats relating to unique identifiers? | The risk management framework applies to all ICANN org risks. The role of the VP, Risk Management (not Enterprise Risk Management) is to facilitate the application of the risk management framework. |  | 2018-09-28
2017-10-09 | Denise via email | 25 | Is there a final DNS risk assessment document (the linked to document is labelled 'draft') https://www.icann.org/en/system/files/files/dns-risk-consultation-28may14-en.pdf, and have there been any updates since 2014? | There is no final document. DNS risk is included in ICANN’s overall risk management. |  | 2018-09-28
2017-10-09 | Denise via email | 27 | The staff report for implementation of SSR1’s Recommendations indicates that this Recommendation is complete. How did staff assess the “comprehensiveness” of the Risk Management Framework to come to this conclusion? | The ICANN organization staff members that were responsible for implementation of this recommendation are no longer with ICANN. Unfortunately, there is no historical record of how they assess “comprehensiveness” of the Risk Management Framework. | 2018-09-30 | 2018-09-26
2017-10-09 | Denise via email | 27 | Please provide details of how the risk management has been staffed since SSR1 recommendations have been adopted by the Board. | Board Risk Committee, Risk Management Committee made up of the ICANN org executive team which provides oversight, VP Risk Management, Function Risk Liaisons who are staff members who represent each function for implementing the risk framework, and all organization personnel who own the risks inherent in their activities. |  | 2018-09-28
2017-08-26 | Denise via email | 2018-01-20 | General Question: What individual within the ICANN organization holds ultimate responsibility for implementation of SSR1 recommendations? | The implementation work and subject matter expertise is distributed across many departments within ICANN organization, and there is no one individual that is able to address questions pertaining to implementation efforts. As such, all follow-up questions pertaining to the implementation of SSR1 Recommendations should be sent to SSR2 staff support using the SSR2 Review Team mailing list ( ssr2-review at icann.org<mailto:ssr2-review at icann.org> ). |  | 2017-07-31 | See email here: http://mm.icann.org/pipermail/ssr2-review/2017-July/000489.html
2017-08-26 | Denise via email | 2018-01-20 | General Question: How has the responsibility for implementation of SSR1 recommendations flowed down through the organization, in terms of ownership, deliverables, performance objectives, etc.? | The implementation work and subject matter expertise is distributed across many departments within ICANN organization, and there is no one individual that is able to address questions pertaining to implementation efforts. As such, all follow-up questions pertaining to the implementation of SSR1 Recommendations should be sent to SSR2 staff support using the SSR2 Review Team mailing list ( ssr2-review at icann.org<mailto:ssr2-review at icann.org> ). |  | 2017-07-31 | See email here: http://mm.icann.org/pipermail/ssr2-review/2017-July/000489.html
2017-08-26 | Denise via email | 2018-01-20 | General Question: What mechanisms exist within the ICANN organization to provide regular (at least annual) reviews of SSR1 implementation, and to make appropriate adjustments to working practices and responsibilities? | In general, once implementation of recommendations are completed they become part of the normal operation of the ICANN organization. As such, they are modified and adjusted operationally, as needed. Some recommendations result in work/reports that have to be revisited on a periodic basis, such as the SSR Framework or SSR budget and expenditure reporting. Such work is revisited as required. | 2018-09-30 | 2018-09-26
2017-08-26 | Denise via email | 2018-01-20 | General Question: What measures of success have been adopted within the ICANN organization for implementation of SSR1 recommendations, and how has the community been involved in defining or reviewing such measures? | One of the issues that ICANN organization highlighted to the SSR2 and other review teams about prior review recommendations, is that recommendations were vague with no clear measures of success identified. As such, the appropriate implementation of each recommendation was very subjective and in some cases, the recommendations were difficult to implement as the objective of the recommendations were not clear. SSR1 recommendations, like those of other prior reviews, were not “SMART” and did not define measures of success. ICANN organization strongly encourages all current review teams to define “SMART” recommendations that are realistic, achievable, have clear objectives and indicate measures of success. | 2018-09-30 | 2018-09-26
2017-08-26 | Denise via email | 2018-01-20 | General Question: How has the ICANN organization ensured that the implementation of SSR1 recommendations are embedded in standard operating procedures? | In general, once implementation of recommendations are completed they become part of the normal operation of the ICANN organization. As such, they are modified and adjusted operationally, as needed. Some recommendations result in work/reports that have to be revisited on a periodic basis, such as the SSR Framework or SSR budget and expenditure reporting. Such work is revisited as required. | 2018-09-30 | 2018-09-26
2017-08-26 | Denise via email | 2018-01-20 | General Question: The SSR1 Report includes check marks for due dates under “Status of Deliverables” and the accompanying text often does not contain completion dates. Please provide a “due date” and completion date for each deliverable. | The Final Implementation Report identifies implementation completion dates for each recommendation, as a whole. Completion dates for each of the listed deliverables are not available. However, we will take on board the suggestion to provide this data on future implementation efforts. On July 26, 2017, we provided the Review Team with a link to the SSR1 Final Implementation Report[community.icann.org]<https://community.icann.org/display/SSR/SSR1+Review+Implementation+Home>, which identifies implementation completion date for each Recommendation, as a whole. |  | 2017-08-25 | See email response for action item 130: http://mm.icann.org/pipermail/ssr2-review/2017-August/000562.html And action item 104: http://mm.icann.org/pipermail/ssr2-review/2017-August/000505.html
2017-06-25 | Geoff during brieifng |  | To what extent do you work with the relevant standards bodies (UNICODE and the IETF) over the issues with the use of IDNs and longer label TLDs? | Staff from the ICANN organization commonly participate in both IETF and UNICODE meetings. In the context of Universal Acceptance, as the community commonly refers to the issues described in this question, the ICANN Community created the Universal Acceptance Steering Group (UASG) which is supported by the ICANN organization. The UASG has its mission to raise awareness and facilitate resolution of Universal Acceptance issues. The ICANN organization is committed to support the efforts of the community through the UASG. |  | 2017-10-06 | Answer provided via email.
2017-06-25 | Noorul as follow-up to briefing |  | There are many challenges in IDN WHOIS lookups. How do we get an accurate IDN WHOIS database for the Incident Handling process? | [Clarification requested from the Review Team via email: Can you please: * Clarify what is meant by "IDN WHOIS database" and by "Incident Handling process”? * Clarify the context in which this question pertains to SSR?]
2017-06-25 | Geoff during brieifng |  | How is the expansion of the name space with more gTLDs contributing to the security and stability of the Internet? | The expansion of the top-level domains is a policy that the community developed and agreed on, and basically it’s a good policy that we implemented. The policy came through the normal multistakeholder process. |  | 2017-06-25 | Answered during meeting 25 June: https://community.icann.org/x/Bw7fAw
2017-06-25 | Geoff during brieifng |  | What metric is being used to ensure a "healthy" DNS marketplace? | I don’t know that there is a correlation between investments in domain names and the security and stability of the domain name system. So, I don’t want to drive any conclusions because I don’t have any data that correlate or actually negate that statement. But at the same time, I think that what we are doing is we are doing our remit, which is promote competition, choice, and innovation in the Domain Name System, and that’s these are actually the guiding principles for why the New gTLD Program was initiated, and I think that it’s very clear the choice is available today that you have more competition in the marketplace and we are starting to see the – well, we saw a lot of innovation in the business models of the TLDs but I think now we’re starting to see the beginning of innovation in the way TLDs are being used and I hear a lot of anecdotal information about plans of what TLDs are coming out with and I think in the next 6 to 12 months, we’re going to see a lot of innovation in that space. So, I think this is you don’t actually freeze everything you do because you want to have security and stability in the marketplace, resiliency in the marketplace. You have to move on both trends. You have to move on the competition choice and innovation as well as you move on the security, stability, and resiliency of the marketplace. So, we have to do both and I think that we are what we we’ve shown here today is that along the way, we are doing a lot more things for the security, stability, and resiliency today than we were doing before the New gTLD Program, and I think that’s the message we’re sending. |  | 2017-06-25 | Answered during meeting 25 June: https://community.icann.org/x/Bw7fAw
2017-06-25 | James during briefing |  | How does ICANN proactively make sure to implement policy (eg. New gTLD Program expansion) in a secure and stable manner? | One aspect of the security and stability and resiliency that we introduced with the New gTLD Program is metered introduction of TLDs to make sure that the stability is not affected. Another area is that there are more obligations in the contracts with the registries. We are moving legacy contracts toward the new gTLD contract because the new gTLD contract has a lot more requirements on the TLDs to be more secure and stable. One example is Specification 11 Section 3(b). This is a requirement of the new gTLD contract that requires the registry operator to periodically conduct a technical analysis to assess whether domains in the TLD are being used to perpetrate security threats, such as pharming, phishing, malware, and botnets. |  | 2017-06-25 | Answered during meeting 25 June: https://community.icann.org/x/Bw7fAw
2017-06-25 | James during briefing |  | New gTLD contract has a lot on New gTLDs to make sure they are secure and stable. To clarify, the main means you see to do that in implementation is through contracts, vs. that as an aspect? Is that the primary means for ICANN to push the SSR remit? | Yes because we don’t have any other tools to use with the registries other than the contract. However, we collaborate with registries on ideas and ways to do things better. There are a lot of different things that we have in the New gTLD Program that we didn’t have before that helped improve the stability of the DNS as a whole. For example Emergency Back-end Registry Operator (EBERO) and the Continuation of Operations Instrument (COI), for which TLDs have to put money aside. If they went down, we can continue to operate the TLD, but not at the expense of the community. |  | 2017-06-25 | Answered during meeting 25 June: https://community.icann.org/x/Bw7fAw
2017-06-25 | James during briefing |  | Can GDD comment on the failures of both SLAM and EBERO where they apply to RSP failure scenarios? Clarification provided by James Gannon: The question was intended to ask why we reach EBERO initiation thresholds (As reported to us in Madrid) multiple times but have never actually followed through on one. This is contrary to best practice that if you have SLAs but do not action based on them then the SLAs themselves become meaningless. I would like further information on what ICANN feels is the actual use case for EBERO as the current model seems to be not based on actual usage. | Per the Base Registry Agreement, the EBERO process is defined in the Registry Transition Processes. One of the main objectives of the EBERO program is to minimize impact on registrants and gTLD users. As of 25 August 2017, we have seen 32 cases in which a service of a gTLD reached one of the emergency thresholds. Of those, 10 cases occurred pre-sunrise, 8 during sunrise, 5 before general availability, and 9 during general availability. The 32 cases involved a total of 211.7k active names at the second level at the time of the cases. The top-five cases in term of registrations that reached emergency thresholds had 211k active domains at the time of cases. Four of those cases happened in 2017. In all of the cases since 2015 the registry operators received compliance notices requiring an explanation of the issue, a root cause analysis and actions required to ensure the same issue would not be repeated. During the emergency, the ICANN organization was in contact with the affected registry/registry service provider to understand the problem at hand. The ICANN organization made a determination that it was going to be faster and had less impact on security and stability to let the current registry/registry service provider to fix the underlying issue than to execute the EBERO transition. Therefore, considering the impact to registrants and users, it was determined the best course of action to not execute an EBERO transition on those cases. |  | 2017-10-06 | Answer provided via email.
2017-06-25 | James during briefing |  | Implementation of EBERO testing took 3 years from implementation of the first new gTLD delegation, no security review of the EBERO’s has ever taken place, what is the justification for that? | The Base Registry Agreement does not specify a review for the EBERO program and it does not require periodic testing. However, since the launch of the new gTLDs and the EBERO program, the ICANN organization has worked with its three EBERO providers to ensure the program is ready to act, should the need arise. Specifically, the EBERO contract requires annual inspection of each of the EBERO providers. Additionally, the ICANN organization has worked with each of their EBERO providers to conduct a full EBERO exercise with a real TLD. These full EBERO exercises have taken advantage of gTLDs that have requested voluntary termination. The ICANN organization obtained consent from the registries to execute these exercises just before the TLD is removed from the root zone. These exercises involved executing the whole set of EBERO activities from the (simulated) failure of a TLD service, to full recovery of the TLD services in the EBERO, including the update of the root zone. Each of the exercises have been successful and provided validation of the readiness of the EBERO program. |  | 2017-10-06 | Answer provided via email
2017-06-25 | James during briefing |  | Can Francisco brief us on both systems (EBERO and SLAM) from an SSR2 perspective (Rather than the SSR1 implementation perspective)? Clarification provided by James Gannon: The original context of the question was brought up during Francisco’s briefing on SSR1 implementation, and thus was looking back on the initial implementation of EBERO, I would like a briefing, or for more information on the current and future security plans for EBERO operators (Such as how ICANN has dealt with CNNIC losing its CA status due to lack of controls over their process and infrastructure) and the further explanations given below on actual planned usage of the EBERO function vs its original concept. | The ICANN organization will be happy to answer other questions you may have to enable the work of SSR2. |  | 2017-10-06 | Answer provided via email
2017-06-25 | James during briefing | 20-22 | I’m also looking for not how much departments are spending but how much their spending on EBERO. | The amount of FY17 Professional Services budget ($2.3m) comprises the following main items: - data escrow services: $930k - WHOIS studies (ARS design/analysis, parsing, accuracy testing, ARS phase 3): $638k - EBERO services: $353k - Background checks for registrar accreditation: $100k The above items add up to $2.0m. The remaining professional services included in the total are miscellaneous smaller items. |  | 2017-06-27 | Question answered via email
2017-06-25 | James during briefing | 9 | Who will be the contracting entity for future SOC2/3 audits of PTI? | It is not currently known who the contractor will be beyond the current period. A competitive RFP process is being conducted to select the vendor for the next SOC2 and SOC3 audits. It is estimated the vendor will be selected in October. |  | 2017-08-09 | Question answered via email:
2017-07-11 | Denise during briefing | 10 | At DNS Symposium in Madrid, a presentation made about SLA indicated that 32 out of the 37 RSP had failed their DNS SLA. Can you please provide more information on this? | * Link to the presentation referenced in the question https://www.icann.org/en/system/files/files/presentation-slam-13may17-en.pdf - slide #23. * The ICANN SLA monitoring system triggers automated escalated alerts to registry operators via the ICANN Contractual Compliance ticketing system for DNS and RDDS failures. Upon resolution of the issue, the Compliance team follows up with the registry operator to find out what happened and the registry operator’s remediation. The reasons for failures (and fixes) vary widely. The Compliance team consults with ICANN Technical Services before closing a ticket to ensure the response is sufficient. * Compliance tracks the SLAM alerts by gTLD not by RSP. * The decision to invoke emergency transition of a TLD (EBERO) is made by the EBERO event directors team. Invoking an EBERO event may not be deemed helpful when the impact is low, such as when there are no registrations or when a registry is responsive and addressing the failure. * If you require more information, please send us the question and we can forward it to the ICANN Technical Services team for a follow-up. |  | 2017-07-13 | Answer provided via email.
2017-07-11 | Denise during briefing | 10 | Regarding WHOIS Bulk submission – what is the use of this tool? | * ICANN has 10 approved users; users can submit up to 300 WHOIS Inaccuracy complaints at a time per submission per week. * During May 2017, ICANN processed a total of 154 tickets initiated from the bulk submission user. This information can be found in the monthly dashboard at this link https://features.icann.org/compliance. |  | 2017-07-13 | Answer provided via email.
2017-07-11 | Denise during briefing | 10 | Recent article about high rate of failure of registrars in an audit conducted by compliance – Share the link to the published report. | Link to the published registrar audit report: https://www.icann.org/resources/pages/compliance-reports-2016 |  | 2017-07-13 | Answer provided via email.
2017-07-11 | Denise during briefing | 10 | What does compliance do regarding enforcement of registry obligations for CZDS? | (CZDS) Zone File Access by Third Parties via the Centralized Zone Data Service Compliance receives complaints alleging that registry operators are not responding to requests for zone file or denying/revoking access for reasons not permitted under the registry agreement. The Registry Agreement is not explicit on when a registry operator must reply to requests for access. ICANN forwards the complaint to the RO and inquires about the pending requests and works toward a resolution of the issue. As for denial or revocation of access, registry operators collaborate with CZDS users to clarify the user’s credentials and usage. However, imposing requirements for access beyond those in the registry agreement and CZDS Terms and Conditions is noncompliant. |  | 2017-07-13 | Answer provided via email.
2017-08-01 | Denise during briefing | 11 | Is there any quantification or more detailed information on what the working relationship with the APWG has yielded? | 1) cross-community collaboration on APWG white papers, see https://apwg.org/resources/apwg-reports/whitepapers, including these topics: - registrar best/recommended practices - web vulnerabilities survey - subdomain registration phishing practices - whois data and phishing - twice annual global phishing surveys 2) cross-posting of SSAC documents for APWG community, again see https://apwg.org/resources/apwg-reports/whitepapers 3) cross-fertilization of subject matter expertise - incoming SSAC chairperson is originally from APWG community - several SSAC members are originally from APWG community - registry (e.g., Afilias, Org) and registrar (Blackknight, GoDaddy) staff have joined APWG 4) Our membership provides access to APWG eCrimeX phishing data for the DAAR project 5) Collaboration on an Accelerated Malicious Domain Suspension program (AMDoS) see https://apwg.org/apwg-news-center/amdos/ for registries and registrars. |  | 2017-08-09 | Answer provided via email