Second Security, Stability, and Resiliency of the Domain Name System Review Team (SSR2)

DRAFT WORKPLAN

Background

The Second Security, Stability, and Resiliency of the Domain Name System Review Team (SSR2) was confirmed in February 2017 and held its first Plenary meeting in March 2017.

This document serves as a guide developed by the SSR2 Review Team as a plan for its work for the review focusing on key areas for discussion and milestones to be achieved during the review process and it will be updated as the work progresses.

| Section 1.0 Preparation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Milestone | Description | Start | Expected Complete | Complete | Status Updates & Notes |
| Determine leadership | Review team will select their own leadership. The designated review team leadership will have responsibilities for managing the work of the review team and determining consensus. | 03-2017 | 03-2017 | 03-2017 | Leadership announced. |
| Determine role of observers | Review team should determine how it would like to obtain input and feedback from its observers. Eg. Observers given time on meeting agendas to speak? How should written input be considered? | 03-2017 | 04-2017 | 05-2017 | Details located on decicated Observers wiki page |
| Adopt legal docs (Conflict of Interest policy, NDA, Statement of Interest) | Review Team to sign Non-Disclosure Agreement, Confidential Disclosure Framework (pursuant to ICANN Bylaws ‐ Section 4.6 (a)(vi)(A) Confidential Disclosure to Review Teams), and to provide duly completed Statement of Interests. | 03-2017 |  |  |  |
| Develop methodology to prioritize issues to be addressed in scope, including validating issues against ICANN Bylaws | Objectives should be set forth in priority order and accompanied by a description of prioritization criteria applied by the Review Team, including an assessment against ICANNs limited Mission and Scope | 05-2017 |  |  |  |
| Adopt scope of work | Adopt a framework that identifies the prioritized focus of the work to be performed by the Review Team | 05-2017 |  |  |  |
| Adopt Terms of Reference (ToR) | The review team should come to agreement on the Terms of Reference and ensure they share a common understanding of the scope of the review, definitions to use, associated work plan and desired output. In doing so, the review team shall consider comments about scope provided by Supporting Organizations and Advisory Committees during the selection process, as appropriate. | 04-2017 | 05-2017 | 05-2017 | Adopted Terms of Reference shared with Board. |
| Adopt Work Plan | Identify steps and details for the work to be performed and estimated dates for when the work will be completed. Progress towards time-bound milestones defined in the work plan shall be tracked and published on Fact Sheet. | 04-2017 |  |  |  |
| Communicate adoption of ToR and Work Plan with ICANN Board | Per ICANN Board Resolution 3 February 2017: The ICANN Board requests that this team develop and deliver to the Board their approved Terms of Reference and Work Plan by the 30th of March, to ensure that the team's scope and timeline is consistent with the requirements of the ICANN Bylaws. | 05-2017 | 05-2017 | 05-2017 | Email sent to Chair of the Board. ICANN Board comments on the Terms of Reference of the Second Security, Stability, and Resiliency of the DNS Review Team (SSR2) |
| Define Review Team project management roles and responsibilities, including budget management | Identify Review Team member(s) responsible for liaising with ICANN organization on budget management, on project management and work plan tracking. | 04-2017 | 05-2017 | 05-2017 |  |
| Identify need for and deliver a proposal on division of work | The Review Team can create as many sub-teams as it deems necessary, through its standard decision process, to complete its tasks. | 04-2017 | 06-2017 | 06-2017 | Subtopics and work items identified. |
| Determine requirements for consultant/independent expert and – if necessary – develop statement of work | Determine if the review team members have the resources and expertise to conduct the work themselves or if additional resources are needed. | 05-2017 | 08-2017 |  |  |
| Develop and adopt outreach plan | Develop a communications and engagement plan that includes calls for input on Review Team work | 05-2017 |  |  | Draft outreach list in development |

| Section 2.0 Research and Studies |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Milestone | Description | Start | Expected Complete | Complete | Status Updates and Notes |
| Assemble repository of background materials | ICANN organization to assemble |  | On-going |  | Available on dedicated wiki page here. ICANN organization to continue populating, as needed |
| Identify briefings/data sources needed | The group shall identify the types and instances of data sources that are deemed needed, important, or useful to this review. |  |  |  |  |
| Identify research needs and develop requirements to address needs | The group shall identify any research needed and provide any speficic requirements that are deemed needed, important, or useful to this review. |  |  |  |  |
| If applicable, assess previous Review Team’s Recommendations and associated Implementation Report | SSR1 Implemention Briefings | 05-2017 | 12-2017 |  |  |
| Identify expert resouces for outreach and data gathering | The group shall identify the expert communities and organizations that are deemed needed, important, or useful to contact for this review. | 04-2017 |  |  | List of organizations assembled for outreach |
| Determine requirements for consultant/independent expert and – if necessary – develop requirements, scope of work, and deliverables | Review team to determine if members have the resources and expertise to conduct the work themselves or if additional resources are needed. | 06-2017 | 08-2017 |  |  |

| Section 3.0 Subteams |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Milestone | Description | Start | Expected Complete | Complete | Status Updates and Notes |
| Sugroups formed | The RT agrees to form subgroups |  |  |  |  |
| SSR1 Review |  |  |  |  |  |
| Select Members of the Subgroup and determine Rapporteur | The full RT to finalize the members of the subteam | 05-2017 |  | 06-2017 | Members: - Alain Patrick Aina - Rapporteur - Denise Michel - Ram Krishna Pariyar |
| Establish Manadate, Objectives and timeline for the work | The group will be responsible for reviewing the implementation of the first Security, Stability and Resiliency (SSR1) Review Team's work and drafting a document outlining the effectiveness of said implementation. |  |  |  |  |
| Identify Subgroup Objectives and Timeline |  |  |  |  |  |
| Determine topics and questions for investiagion |  |  |  |  | See https://docs.google.com/document/d/1DWoT4VoMlT5Dvcy78EXI-O5tQFqa9CblwsDEV6go51s/edit |
| Validate topics against ICANN Bylaws | Assess identified topics against ICANNS limited Mission and Scope, and bylaw requirements to determine if within scope to proceed. |  |  |  |  |
| Adopt Work Plan | Identify steps and details for the work to be performed and estimated dates for when the work will be completed. Progress towards time-bound milestones | 06-2017 | 08-2017 |  | See: https://community.icann.org/display/SSR/Subgroup+%231+-+SSR1+Review |
| Conduct investigation of identified objectives |  |  |  |  |  |
| Determine if specific research is needed |  |  |  |  |  |
| Determine if Independent Expert is needed |  |  |  |  |  |
| Prepare draft report, including proposed recommendations that follow the S.M.A.R.T. model, and include metics to assist with implementation |  |  |  |  |  |
| Present subgroup report and proposed recommendtions to RT |  |  |  |  |  |
| ICANN SSR |  |  |  |  |  |
| Select Members of the Subgroup and determine Rapporteur | The full RT to finalize the members of the subteam | 05-2017 |  | 06-2017 | Members: - Boban Krsic - Rapporteur - Denise Michel - James Gannon - Kerry-Ann Barrett - Noorul Ameen - Žarko Kecić |
| Establish Manadate, Objectives and timeline for the work | The group will be responsible for reviewing the completeness and effectiveness of ICANNs internal security processes and the effectiveness of the ICANN security framework. |  |  |  |  |
| Identify Subgroup Objectives and Timeline |  |  |  |  |  |
| Determine topics and questions for investiagion |  |  |  |  | See https://docs.google.com/document/d/1DWoT4VoMlT5Dvcy78EXI-O5tQFqa9CblwsDEV6go51s/edit |
| Validate topics against ICANN Bylaws | Assess identified topics against ICANNS limited Mission and Scope, and bylaw requirements to determine if within scope to proceed. |  |  |  |  |
| Adopt Work Plan | Identify steps and details for the work to be performed and estimated dates for when the work will be completed. Progress towards time-bound milestones | 06-2017 | 08-2017 |  | See https://community.icann.org/display/SSR/Subgroup+%232+-+ICANN+SSR |
| Conduct investigation of identified objectives |  |  |  |  |  |
| Determine if specific research is needed |  |  |  |  |  |
| Determine if Independent Expert is needed |  |  |  |  |  |
| Prepare draft report, including proposed recommendations that follow the S.M.A.R.T. model, and include metics to assist with implementation |  |  |  |  |  |
| Present subgroup report and proposed recommendtions to RT |  |  |  |  |  |
| DNS SSR |  |  |  |  |  |
| Select Members of the Subgroup and determine Rapporteur | The full RT to finalize the members of the subteam | 05-2017 |  | 06-2017 | Members: - Geoff Huston - Rapporteur - Alain Patrick Aina - Cathy Handley - Jabhera Matogoro - Ram Krishna Pariyar - Don Blumenthal - Mohamad Amin Hasbini - Eric Osterweil - Boban Krsic - Žarko Kecić |
| Establish Manadate, Objectives and timeline for the work | The group will be responsible for reviewing ICANNs role in the broader security of the DNS and unique identifiers system, including its role in mitigating threats to the DNS and other unique identities it coordinates. |  |  |  |  |
| Identify Subgroup Objectives |  |  |  |  |  |
| Determine topics and questions for investiagion |  | 07-2017 |  |  | See Google Doc https://docs.google.com/document/d/1HcwcIPhdN3Ogad0zqR7vM5IVyrio6sxCWQF7RGpxoHI/edit#heading=h.gjdgxs |
| Validate topics against ICANN Bylaws | Assess identified topics against ICANNS limited Mission and Scope, and bylaw requirements to determine if within scope to proceed. |  |  |  |  |
| Adopt Work Plan | Identify steps and details for the work to be performed and estimated dates for when the work will be completed. Progress towards time-bound milestones | 06-2017 | 08-2017 |  |  |
| Conduct investigation of identified objectives |  |  |  |  |  |
| Determine if specific research is needed |  |  |  |  |  |
| Determine if Independent Expert is needed |  |  |  |  |  |
| Prepare draft report, including proposed recommendations that follow the S.M.A.R.T. model, and include metics to assist with implementation |  |  |  |  |  |
| Present subgroup report and proposed recommendtions to RT |  |  |  |  |  |
| Future Challenges |  |  |  |  |  |
| Select Members of the Subgroup and determine Rapporteur | The full RT to finalize the members of the subteam | 05-2017 |  | 06-2017 | Members: - Kerry-Ann Barrett - Rapporteur - Denise Michel - Eric Osterweil - Jabhera Matogoro - Mohamad Amin Hasbini - Noorul Ameen |
| Establish Manadate, Objectives and timeline for the work | The group will be responsible for reviewing the long term strategy of ICANN to plan for and mitigate potential threats to the secure and resilient operation of the unique identifiers systems it coordinates. |  |  |  |  |
| Identify Subgroup Objectives and Timeline |  |  |  |  |  |
| Determine topics and questions for investiagion |  |  |  |  | See https://docs.google.com/document/d/1DWoT4VoMlT5Dvcy78EXI-O5tQFqa9CblwsDEV6go51s/edit |
| Validate topics against ICANN Bylaws | Assess identified topics against ICANNS limited Mission and Scope, and bylaw requirements to determine if within scope to proceed. |  |  |  |  |
| Adopt Work Plan | Identify steps and details for the work to be performed and estimated dates for when the work will be completed. Progress towards time-bound milestones | 06-2017 | 08-2017 |  |  |
| Conduct investigation of identified objectives |  |  |  |  |  |
| Determine if specific research is needed |  |  |  |  |  |
| Determine if Independent Expert is needed |  |  |  |  |  |
| Prepare draft report, including proposed recommendations that follow the S.M.A.R.T. model, and include metics to assist with implementation |  |  |  |  |  |
| Present subgroup report and proposed recommendtions to RT |  |  |  |  |  |
| IANA Transition |  |  |  |  |  |
| Select Members of the Subgroup and determine Rapporteur | The full RT to finalize the members of the subteam | 05-2017 |  | 06-2017 | Members: - James Gannon - Rapporteur - Cathy Handley - Eric Osterweil - Geoff Huston |
| Establish Manadate, Objectives and timeline for the work | The group will be responsible for reviewing the impact of the IANA transition on the security of ICANN and the unique identifier systems it coordinates. |  |  |  |  |
| Identify Subgroup Objectives and Timeline |  |  |  |  |  |
| Determine topics and questions for investiagion |  |  |  |  | See https://docs.google.com/document/d/1DWoT4VoMlT5Dvcy78EXI-O5tQFqa9CblwsDEV6go51s/edit |
| Validate topics against ICANN Bylaws | Assess identified topics against ICANNS limited Mission and Scope, and bylaw requirements to determine if within scope to proceed. |  |  |  |  |
| Adopt Work Plan | Identify steps and details for the work to be performed and estimated dates for when the work will be completed. Progress towards time-bound milestones | 06-2017 | 08-2017 |  | See: https://trello.com/b/CLrY87hn/ssr2-subtopic-5-iana-transition |
| Conduct investigation of identified objectives |  |  |  |  |  |
| Determine if specific research is needed |  |  |  |  |  |
| Determine if Independent Expert is needed |  |  |  |  |  |
| Prepare draft report, including proposed recommendations that follow the S.M.A.R.T. model, and include metics to assist with implementation |  |  |  |  |  |
| Present subgroup report and proposed recommendtions to RT |  |  |  |  |  |

| Section 4.0 Draft Report |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Milestone | Description | Start | Expected Complete | Complete | Status Updates and Notes |
| Assemble findings | The Review Team, after completing its research and studies, shall draw initial conclusions and endeavor to produce findings. |  |  |  |  |
| Develop and adopt template for findings and recommendations | Information will be made available for the Review Team’s reference on how to approach development of a SMART and implementable recommendation. |  |  |  |  |
| Seek Board Caucus group and ICANN organization’s input on findings | Engage with ICANN organization and ICANN Board Caucus Group, to seek input on findings in development under the agreed scope |  |  |  |  |
| Consolidate findings and assemble draft recommendations | Draft recommendations may arise from initial findings. Duly complete templates adopted by Review Team |  |  |  |  |
| Cross-check draft recommendations with scope | Ensure draft recommendations support objectives of the Review and are in line with the agreed-upon scope. |  |  |  |  |
| Seek Board Caucus group and ICANN organization’s input on implementability of draft recommendations | Engage with ICANN organization and ICANN Board Caucus Group, to seek input on feasibility of recommendations under the agreed scope |  |  |  |  |
| Adopt report format | A template is available for the review team’s use. |  |  |  |  |
| Approve draft findings and recommendations | Review Team shall document the rationale they have employed for any recommendations and, where possible, provide a quantitative target or metric for measurement of the recommendations success. |  |  |  |  |
| Approve draft report for public comment | Recommendations that meet the criteria defined above - clear, concise, concrete, prioritized, measurable and implementable will be incorporated into a draft report. The draft report will be published for public comment for a period of at least 40 days. The RDS-WHOIS2-RT may produce additional versions for public comment should it be deemed necessary. |  |  |  |  |

| Section 5.0 Public Comment Period |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Milestone | Description | Start | Expected Complete | Complete | Status Updates and Notes |
| Publish draft report for public comment | A draft report will be published for public comment for a period of at least 40 days. |  |  |  |  |
| Socialize draft recommendations with community | ICANN63, Barcelona and/or webinars |  |  |  |  |

| Section 6.0 Final Report |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Milestone | Description | Start | Expected Complete | Complete | Status Updates and Notes |
| Analysis of public comment | The Review Team will consider public comments and work towards reaching consensus on incorporating public comments, as appropriate, into the final report. Include an explanation of how public comments were considered as well as a summary of changes made in response to public comments. ICANN organization will provide a compilation of the public comments received. |  |  |  |  |
| Assemble final recommendations | The Review Team shall document the rationale they have employed for any nre recommendations and, where possible, provide a quantitative target or metric for measurement of the recommendations’ success. |  |  |  |  |
| Cross-check final draft recommendations with scope | Ensure final draft recommendations support objectives of the Review and is in line with the agreed-upon scope. |  |  |  |  |
| Seek Board Caucus group and ICANN organization’s input on implementability of draft recommendations | Engage with ICANN organization and ICANN Board Caucus Group, to seek input on feasibility of recommendations under the agreed scope |  |  |  |  |
| Approve final findings, recommendations and report for Board consideration | The Review Team will come to an agreement on its final recommendations. The Review Team shall document the rationale they have employed for any recommendations and, where possible, provide a quantitative target or metric for measurement of the recommendation’s success. |  |  |  |  |
| Send final report to ICANN Board | The Review Team will send the final report to the ICANN Board for consideration. |  |  |  |  |

| Section 7.0 Implementation Planning and Feedback |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Milestone | Description | Start | Expected Complete | Complete | Status Updates and Notes |
| Complete ICANN organization survey on review process | Review Team members will be invited to provide input on review process |  |  |  |  |
| Implementation | A subset of Review team members will be determined and may be called upon to provide feedback on the review process and, when appropriate, implementation of recommendations. | --- | --- |  |  |