## Slide 1: Second Security, Stability, and Resiliency of the Domain Name System Review Team (SSR2)
SSR1 review Sub-group activities summary
Alain P. AINA
08/08/2018

## Slide 2: Sub Topic 1 – SSR1 Review
  Topic
  Review of implementation of SSR1 Report
  Related Bylaw
  4.6 (c)(iv)
  Team Members
  Denise, Alain, Ram Krishna - Rapporteur: Alain
Skillset
  ICANN, SSR1, Audit, Project management
Description of activity
  The sub team will be responsible for reviewing the implementation of the SSR1 RTs work and drafting a document outlining the effectiveness of said implementation
  Complete the assessment of the implementation of SSR1 recommendations, the impact of the implementation, how the post implementation is being managed and what implications for the SSR2 review.

## Slide 3: Sub Topic 1 – SSR1 Review
  Work Items
  Assemble data
  Preliminary review of the implementation of the recommendations
  Elaboration ToR for the consultant (for Implementation’s gap analysis)
  Selection of consultant
  Follow up with consultant to ensure work performed as required
  Review consultant report
  Engage the global review team for consultant report approval
  SSR1 recommendations implementation implications on the SSR2 review

## Slide 4: Achievements
Activity | Date | Status
SSR1 briefings by full review team https://community.icann.org/display/SSR/SSR1+Review+Implementation+Home?preview=/54691765/64084717/SSR1%20Recs%201-28%2031March2017.pdf | March 2017 | 
Sub-groups formation SSR1 Implementation review: Do or hire an independent expert for the Gap analysis on the SSR1 recommendations implementation? | May 2017 | 
SSR1 Review - Meeting #1 Thursday, 20 July 2017 21:00 UTC SSR1 Review - Meeting #2 Thursday, 3 August 2017 21:00 UTC - CANCELLED |  | 
RFP for Gap Analysis of Implementation of SSR1 Review Recommendations published https://www.icann.org/news/announcement-2-2017-09-28-en | September 2017 | 
Only 2 proposals received (16/04/2017) and extension was agreed to November (07/11/2017) | October 2017 | 
Things got paused: Some criticisms from community about hiring an independent expert for the Gap analysis |  |