SSR2 Plenary Meeting #18 - Tuesday 11 July @ 21:00 UTC

NOTE: The official record of the meeting can be found on the SSR2 wiki here.

| Plenary Action Items/Requests #18 |  |  |
| --- | --- | --- |
| Action/Request | Owner | Expected Completion Date |
| Share link to the published ICANN Compliance Audit Report. | ICANN Org | 14 July |
| Provide follow-up questions via email regarding the SSR1 implementation briefing by ICANN Compliance – recommendation 10. | SSR2-RT | 18 July |
| Respond to questions asked by the Review Team during the SSR1 implementation briefing by ICANN Compliance – recommendation 10. | ICANN Org | 25 July |

| Subgroup Action Items/Requests #18 |  |  |
| --- | --- | --- |
| Action/Request | Owner | Expected Completion Date |
| SSR1: Review work items circulated via email indicate which ones are out of scope, which ones are missing. | SSR1 Implementation Subteam | 21 July |
| SSR1: Schedule call to finalize work items, agree on methodology and set timelines. | SSR1 Implementation Subteam, ICANN Org | 17 July |
| ICANN SSR: Review ICANN SSR re-organized work items (37 items in 8 groups) and send feedback to ICANNsecurity-SSR2-RT@icann.org. | SSR2-RT | 25 July |
| DNS SSR: Work with DNS SSR subteam to set up a call early next week or next. | ICANN Org | 14 July |
| DNS SSR: Schedule a call to review work items and scope. | DNS SSR Subteam, ICANN Org | 17 July |
| Future Challenges: Team is invited to provide comments/edits to the work items Google document and add to brainstorming document. | SSR2-RT | 25 July |

SUMMARY NOTES:

Updated SOIs & note apologies/absences

- Apologies – Emily Taylor, Geoff Huston, Don Blumenthal (James delayed)

- No updated SOIs

- Changes to the agenda order – SSR1 recommendation to begin with.

SSR1 Implementation Briefing: Maguy Serad, VP ICANN Compliance (Recommendation 10)

- Summary presentation of implementation of recommendation 10.

- Q&A

- Team to provide follow-up questions via email.

Johannesburg meeting – recap & review of action items

- Review of open and recently closed action items.

- Briefings to note for future agenda items: 1. Framework for Registry Operators to Respond to Security Threats and 2. DNS Abuse study. Co-Chairs will work with staff to coordinate.

- Note deadline for DNS Abuse study is now mid-August.

Updates from subtopic teams

- SSR1 Implementation

  - Alain sent an email to the list asking for the team to review the work items and indicate which ones are out of scope, which ones are missing. The team can then have a call to finalize the work items and methodology

- ICANN Security:

  - Team to Review ICANN SSR re-organized work items (37 items in 8 groups) and send feedback to ICANNsecurity-SSR2-RT@icann.org.

- DNS Security

  - Team agreed in Johannesburg to rename to DNS SSR.

  - Eric has some questions and comments on the draft, will circulate a summary via email and address on the next subteam call.

  - Staff to help team set up a subteam call early next week, or the week after due to IETF.

- Future Challenges

  - Team is invited to provide comments/edits to the work items Google document and add to brainstorming document.

- IANA Transition

  - First round of discussions with Elise and Kim complete. Cathy is writing up outcomes from face-to-face meeting and next steps.

AOB

- None

END OF MEETING