## SSR1 Recommendations
SSR Framework
1 | ICANN should publish a single, clear, and consistent statement of its SSR remit and limited technical mission.
|  | Evaluate the statement |  | PL | 0
7 | ICANN should build on its current SSR Framework by establishing a clear set of objectives and prioritizing its initiatives and activities in accordance with these objectives.
|  | Review objectives, initiatives and activities defined in SSR Framework |  | PL, TE, IS | 0
SSR-related priorities, objectives and activities are reported on regularly as part of SOP
Restored process for establishing updated SSR priorities and objectives
8 | ICANN should continue to refine its Strategic Plan objectives, particularly the goal of maintaining and driving DNS availability. Clear alignment of Framework & Strategic Plan.
|  | Review of Strategic Plan objectives and alignment of SR Framework with Strategic Plan |  | PL, TE, IS | 0
Incorporation and reflection of SSR Framework and SSR priorities, objectives and activities into ICANN plans and budgets
Progress reporting on SSR-related priorities, objectives and activities
11 | ICANN should finalize and implement measures of success for new gTLDs and IDN fast track that expressly relate to its SSR-related program objectives, including measurements for the effectiveness of mechanisms to mitigate domain name abuse.
|  | Review and analyze |  | TE, IS, BP | 0
Measures for new gTLD program and IDN fast track related to SSR objectives
Status of security and stability mechanism for gTLD program and IDN fast track
18 | ICANN should conduct an annual operational review of its progress in implementing the SSR Framework and include this assessment as a component of the following year’s SSR Framework
|  | Analyze annual review of SSR Framework implementation |  | BP, TE, IS | 0
Analyze process for implementation and update of SSR Framework
Review how assessment is incorporated in the following year SSR Framework
19 | ICANN should establish a process that allows the Community to track the implementation of the SSR Framework. Information should be provided with enough clarity that the Community can track ICANN’s execution of its SSR responsibilities.
|  | Review the process for tracking the implementation of SSR Framework |  | BP, TE, IS | 0
Review tracking mechanism
Review of the possibilities that the Community has for tracking ICANN's execution of its SSR responsibility
Analyze the clarity of provided information
20 | ICANN should increase the transparency of information about organization and budget related to implementing the SSR Framework and performing SSR-related functions.
|  | Review transparency of information related to organization and budget in regard of SSR functions |  | PL, BP | 0
Analyze planning framework and process
Analyze mechanism for providing public information on SSR related activities
21 | ICANN should establish a more structured internal process for showing how organization and budget decisions relate to the SSR Framework, including the underlying cost-benefit analysis.
|  | Analyze internal process for organization and budget decisions related to SSR Framework implementation |  | PL, BP | 0
Analyze internal decision making processes
Analyze underlaying analysis including cost-benefit
22 | ICANN should publish, monitor and update documentation on the organization and budget resources needed to manage SSR issues in conjunction with introduction of new gTLDs.
|  | Review documentation on the organization and budget resources needed to manage SSR issues |  | PL, BP | 0
Review publishing and update process
Review monitoring process
ICANN’s SSR Role & Remit Within It’s Limited Mission
2 | ICANN’s definition and implementation of its SSR remit and limited technical mission should be reviewed in order to maintain consensus and elicit feedback from the Community.
|  | ICANN Planning process (recurring) |  | PL, TE, BP, RA | 0
Strategic plan for FY2016 – 2020
Five-Year Operating plan and analyze KPIs
Annual Operating plan
Achievements and Progress Reports
Review stakeholder and community comments
3 | Once ICANN issues a consensus-based statement of its SSR remit and limited technical mission, ICANN should utilize consistent terminology and descriptions of this statement in all materials.
|  | Review terminology |  | PL, IS, TE | 0
ICANN Security Terminology
ICANN Glossary
9 | ICANN should assess certification options with commonly accepted international standards (e.g. ITIL, ISO and SAS-70) for its operational responsibilities. ICANN should publish a clear roadmap towards certification.
|  | Review ICANN certification status |  | PL, IS, BP | 0
Review ICANN roadmap towards certification
Certification status
24 | ICANN must clearly define the charter, roles and responsibilities of the Chief Security Office Team.
|  | Review definition of roles and responsibilities of CIO team regarding SSR |  | PL, TE, IS | 0
Review roles and responsibilities associated to SSR of the Internet unique identifiers systems
Review how CIO team focus on current and future threats
25 | ICANN should put into place mechanisms for identifying both near and longer-term risks and strategic factors in its Risk Management Framework.
|  | Analyze ICANNs Risk Management Framework |  | RA, TE, IS | 0
Review Risk Management Framework
Analyze risk assessments, mitigation plans assessment and risk governance
Review Report on Mitigating Risk of Name Collisions
26 | ICANN should prioritize the timely completion of a Risk Management Framework.
|  | Covered in Recommendation 25 |  | RA, TE, IS
27 | ICANN’s Risk Management Framework should be comprehensive within the scope of its SSR remit and limited missions.
|  | Covered in Recommendation 25 |  | RA, TE, IS
SSR Relationships to Support ICANN’s Work
4 | ICANN should document and clearly define the nature of the SSR relationships it has within the ICANN Community in order to provide a single focal point for understanding the interdependencies between organizations.
|  | Review definitions of SSR relationships within ICANN Community |  | PL, BP | 0
ISSSR Team SOP work based on SSR activities
SSR-related elements of MOUs
Formal relationships ICANN has with key organizations
5 | ICANN should use the definition of its SSR relationships to maintain effective working arrangements and to demonstrate how these relationships are utilized to achieve each SSR goal.
|  | How relationships within ICANN Community is utilzed |  | PL, TE, BP | 0
Review Report on ICANN’s progress toward SSR-related KSFs and KPIs involving SSR relationships
Review information on how key relationships noted in Recommendation 4 are used to achieve SSR goals
SSR Community Outreach & Info Sharing – Security Threats & Mitigation
6 | ICANN should publish a document clearly outlining the roles and responsibilities for both the SSAC and RSSAC in order to clearly delineate the activities of the two groups. ICANN should seek consensus for this across both groups, recognizing the history and circumstances of the formation of each. ICANN should consider appropriate resourcing for both groups, consistent with the demands placed upon them.
|  | Review ICANN documents regarding SSAC and RSSAC responsibilities |  | PL, TE, IS | 0
Roles and responsibilities of SSAC in ICANN’s Bylaws and defined in SSAC’s Operating Procedures
Roles and responsibilities for RSSAC in an updated charter contained in ICANN’s Bylaws
12 | ICANN should work with the Community to identify SSR-related best practices and support the implementation of such practices through contracts, agreements and MOUs and other mechanisms.
|  | Review interaction with the Community in identifying SSR best practices |  | PL, TE, IS | 0
Identification and communication of SSR-related best practices
Implementation of SSR-related best practices through contracts, agreements and MOUs and other mechanisms
13 | ICANN should encourage all Supporting Organizations to develop and publish SSR-related best practices for their members.
|  | Review and analyze SO development of SSR related best practices |  | TE, IS | 0
Review ICANN activities in ecouraging SO to develop SSR best practices
Review SO activities in developing and publishing SSR best practices
14 | ICANN should ensure that its SSR-related outreach activities continuously evolve to remain relevant, timely and appropriate.
|  | Review SSR related outreach activities |  | TE, IS, RA | 0
Review ICANN SSR related outreach activities (regional coverage)
Review relevance and appropriateness of SSR related activities
15 | ICANN should act as a facilitator in the responsible disclosure and dissemination of DNS security threats and mitigation techniques.
|  | Review ICANN activities in disclosing and disseminating DNS security threats and mitigation techniques |  | TE, IS, RA | 0
Reiew ICANN activities
Review of disclosed DNS threats and mitigation techniques
16 | ICANN should continue its outreach efforts to expand Community participation and input into the SSR Framework development process. ICANN also should establish a process for obtaining more systematic input from other ecosystem participants.
|  | Analyze ICANN outreach efforts in expanding Community participation into SSR Framework development process |  | TE, IS, BP | 0
Review ICANN activities in expanding Community participation
Review process for obtaining imput from Community
Review outcomes of capability-building initiatives
23 | ICANN must provide appropriate resources for SSR-related Working Groups and Advisory Committees, consistent with the demands placed upon them. ICANN also must ensure decisions reached by Working Groups and Advisory Committees are reached in an objective manner that is free from external or internal pressure.
|  | Analyze resources allocated for SSR related WGs and ACs and allocation process |  | PL, TE, IS | 0
Analyze does ICANN provide appropriate resources for WGs and ACs
Review of established processes and procedures for WGs and ACs resource allocation
Analyze whether the allocation of resources is done in an objective manner that is free of external or internal pressure
28 | ICANN should continue to actively engage in threat detection and mitigation, and participate in efforts to distribute threat and incident information.
|  | Review ICANN engagement in threat detection and mitigation |  | TE, IS, BP | 0
Review how ICANN engage in threat detection and mitigation
Review Coordinated Vulnerability Disclosure Reporting at ICANN
Review other ways of engagement
Compliance
10 | ICANN should continue its efforts to step up contract compliance enforcement and provide adequate resources for this function. ICANN also should develop and implement a more structured process for monitoring compliance issues and investigations.
|  | Review of contract compliance |  | PL | 0
Analyze efforts and resource for contract compliance
Review contract compliance enforcement and monitoring procedures
Note on B62: Zarko Kecic: Should be covered within subgroup2