## SSR2 Workplan
Second Security, Stability & Resiliency of the DNS Review Team (SSR2) - Work Plan following Restart
The Second Security, Stability, and Resiliency of the Domain Name System (SSR2) Review Team was confirmed in February 2017 and held its first Plenary meeting in March 2017. Its work was suspended by the ICANN Board in October 2017, and restarted in June 2018. This work plan subsequently was updated to reflect the work of SSR2 Review Team post-suspension, and previous work plans are archived on the SSR2 wiki. This work plan serves as a guide developed by the SSR2 Review Team as a plan for its work for the review focusing on key areas for research and discussion and related milestones to be achieved during the review process. The work plan is expected to evolve with the Review Team's work and will be updated as the work progresses. Dates reflect a typical Review lifecycle, but are to be adjusted by the Review Team, based upon their agreed-upon scope and the effort required to address highest-priority objectives within available budget and time.
At Risk | Task Name | Start Date | End Date | Assigned To | Duration (days) | % Complete | Predecessors | Comments
| Restart Review Team |  |  |  | 230 | 100%
| Appoint new members of SSR2 review team | 2017-10-31 | 2018-06-18 | SO/AC Leaders | 231 | 100%
| Restart Review Team | 2017-10-31 | 2018-06-18 | ICANN Board | 231 | 100%
| Plan Review |  |  |  | 122 | 100%
| Determine leadership | 2018-08-22 | 2018-08-24 | SSR2-RT | 3 | 100%
| Adopt and publish Terms of Reference | 2018-08-24 | 2018-08-29 | SSR2-RT | 6 | 100%
| Adopt and publish Workplan | 2018-09-01 | 2018-11-13 | SSR2-RT | 74 | 100%
| Send adopted ToR to ICANN Board | 2018-09-05 | 2018-09-05 | SSR2-RT | 1 | 100%
| Develop and adopt outreach plan | 2018-09-01 | 2018-09-13 | SSR2-RT | 13 | 100%
| Develop and adopt template for findings and recommendations | 2018-10-25 | 2018-12-21 | SSR2-RT | 58 | 100%
| Research and Studies |  |  |  | 232 | 100%
| Complete repository of background materials | 2018-06-07 | 2019-01-24 | ICANN org | 232 | 100%
| Identify further briefings / data sources needed | 2018-06-07 | 2019-01-24 | SSR2-RT | 232 | 100%
| Receive answers from ICANN staff, and generate any follow-up queries | 2018-06-07 | 2019-01-24 | ICANN org / SSR2-RT | 232 | 100%
| Conduct Review |  |  |  |  | 48.67%
Workstreams
| Workstream 1 - SSR1 Evaluation of implementation |  |  |  | 271 | 83.33%
| Workplan Execution |  |  |  |  | 100%
| Produce Gap analysis outline and present to review team for input | 2018-09-10 | 2018-09-30 | SSR2-RT | 21 | 100%
| Review, analyze and summarize relevant documentation | 2018-06-18 | 2018-11-02 | SSR2-RT | 138 | 100%
| Conduct further interviews as appropriate | 2018-09-01 | 2018-10-15 | SSR2-RT | 45 | 100%
| Draft summary note of key findings of the review of SSR1 recommendations | 2018-10-21 | 2018-11-16 | SSR2-RT | 27 | 100%
| Prepare Draft Report Section |  |  |  |  | 66.67%
| Approve findings | 2018-10-21 | 2019-02-14 | SSR2-RT | 117 | 100%
| Assemble draft recommendations using the designated Review Team template | 2018-10-21 | 2019-02-14 | SSR2-RT | 117 | 100%
| Cross-check draft recommendations with scope and Bylaws | 2019-03-01 | 2019-03-15 | SSR2-RT | 15 | 0%
| Workstream 2 - ICANN SSR |  |  |  | 207 | 32.5%
| Workplan Execution |  |  |  |  | 65%
| Review, analyze and summarize relevant documentation & touchbase on the current status of the workstream progress | 2018-11-01 | 2019-01-15 | SSR2-RT | 76 | 100%
| Conduct investigation of identified objectives | 2018-11-01 | 2019-03-01 | SSR2-RT | 121 | 80%
| Conduct relevant interviews as appropriate | 2018-11-01 | 2019-03-01 | SSR2-RT | 121 | 80%
| Answer follow-up questions | 2019-02-01 | 2019-02-15 | ICANN Org | 15 | 0%
| Draft summary note of key findings | 2019-03-01 | 2019-03-15 | SSR2-RT | 15 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2019-03-16 | 2019-05-19 | SSR2-RT | 65 | 0%
| Assemble draft recommendations using the designated Review Team template | 2019-03-16 | 2019-05-19 | SSR2-RT | 65 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2019-05-19 | 2019-05-26 | SSR2-RT | 8 | 0%
| Workstream 3 - DNS SSR |  |  |  | 245 | 24.38%
| Workplan Execution |  |  |  |  | 48.75%
| Review, analyze and summarize relevant documentation & touchbase on the current status of the workstream progress | 2018-10-01 | 2019-02-03 | SSR2-RT | 126 | 90%
| Conduct investigation of identified objectives | 2018-10-01 | 2019-04-01 | SSR2-RT | 183 | 75%
| Conduct relevant interviews as appropriate | 2018-10-01 | 2019-03-15 | SSR2-RT | 166 | 30%
| Answer follow-up questions | 2019-02-07 | 2019-02-22 | ICANN Org | 16 | 0%
| Draft summary note of key findings | 2019-03-16 | 2019-05-19 | SSR2-RT | 65 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2019-02-22 | 2019-03-16 | SSR2-RT | 23 | 0%
| Assemble draft recommendations using the designated Review Team template | 2019-05-19 | 2019-05-26 | SSR2-RT | 8 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2019-05-26 | 2019-06-02 | SSR2-RT | 8 | 0%
| Workstream 4 - Future Challenges |  |  |  | 184 | 28.12%
| Workplan Execution |  |  |  |  | 56.25%
| Review, analyze and summarize relevant documentation & touchbase on the current status of the workstream progress | 2018-12-01 | 2019-03-15 | SSR2-RT | 105 | 50%
| Conduct investigation of identified objectives | 2018-12-01 | 2019-03-15 | SSR2-RT | 105 | 75%
| Conduct relevant interviews as appropriate | 2018-12-01 | 2019-01-27 | SSR2-RT | 58 | 100%
| Answer follow-up questions | 2019-01-31 | 2019-02-14 | ICANN Org | 15 | 0%
| Draft summary note of key findings | 2019-03-16 | 2019-05-19 | SSR2-RT | 65 | 0%
| Prepare Draft Report Section |  |  |  |  | 0%
| Approve findings | 2019-02-22 | 2019-03-16 | SSR2-RT | 23 | 0%
| Assemble draft recommendations using the designated Review Team template | 2019-05-19 | 2019-05-26 | SSR2-RT | 8 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2019-05-26 | 2019-06-02 | SSR2-RT | 8 | 0%
| Workstream 5 - IANA Transition (not going forward) |  |  |  | 684 | 75%
| Workplan Execution |  |  |  |  | 75%
| Review, analyze and summarize relevant documentation & touchbase on the current status of the workstream progress | 2017-05-01 | 2017-08-04 | SSR2-RT | 96 | 100%
| Conduct investigation of identified objectives | 2017-06-01 | 2017-08-04 | SSR2-RT | 65 | 100%
| Conduct relevant interviews as appropriate | 2017-07-01 | 2017-08-04 | SSR2-RT | 35 | 100%
| Prepare draft report note re not going forward with this work | 2018-10-25 | 2019-03-15 | SSR2-RT | 142 | 0%
| Draft Report |  |  |  | 245 | 0%
| Administrative Duties |  |  |  |  | 0%
| Adopt report format | 2019-02-22 | 2019-03-15 | SSR2-RT | 22 | 0%
| Internal Review |  |  |  |  | 0%
| Review workstream outputs and proposed recommendations | 2019-03-15 | 2019-05-19 | SSR2-RT | 66 | 0%
| Cross-check draft recommendations with scope and Bylaws | 2019-05-19 | 2019-05-25 | SSR2-RT | 7 | 0%
| Pre-approve draft recommendations | 2019-05-19 | 2019-05-25 | SSR2-RT | 7 | 0%
| Outreach |  |  |  |  | 0%
| Seek Board Caucus group and ICANN organization’s input and feasability assessment on draft recommendations | 2019-05-25 | 2019-06-27 | SSR2-RT | 34 | 0%
| Seek Community’s input on implementability of draft recommendations | 2019-05-25 | 2019-06-27 | SSR2-RT | 34 | 0%
| Assembling Draft Report |  |  |  |  | 0%
| Produce Draft Report | 2019-06-27 | 2019-07-27 | SSR2-RT | 31 | 0%
| Approval process |  |  |  |  | 0%
| Approve draft findings and recommendations | 2019-07-27 | 2019-08-10 | SSR2-RT | 15 | 0%
| Approve draft report for public comment | 2019-07-27 | 2019-08-10 | SSR2-RT | 15 | 0%
| Publishing Draft Report |  |  |  |  | 0%
| Send approved draft report sections to language services | 2019-08-10 | 2019-08-10 | ICANN org | 1 | 0%
| Public Comment and Outreach on Draft Report |  |  |  |  | 0%
| Socialize draft recommendations with community | 2019-08-10 | 2019-10-10 | SSR2-RT | 62 | 0%
| Publish draft report for public comment | 2019-08-10 | 2019-10-10 | ICANN org | 62 | 0%
| Produce summary of public comments | 2019-10-10 | 2019-10-24 | ICANN org | 15 | 0%
| Adopt public comment summary for publication | 2019-10-24 | 2019-10-24 | SSR2-RT | 1 | 0%
| Final Report |  |  |  | 15 | 0%
| Update Draft Report |  |  |  |  | 0%
| Assemble final recommendations and update draft report based on public comments received | 2019-10-24 | 2019-11-07 | SSR2-RT | 15 | 0%
| Cross-check final recommendations with scope and Bylaws | 2019-10-24 | 2019-11-07 | SSR2-RT | 15 | 0%
| Approval process |  |  |  |  | 0%
| Approve final findings, recommendations and report for Board consideration | 2019-10-24 | 2019-11-07 | SSR2-RT | 15 | 0%
| Send Final Report |  |  |  |  | 0%
| Send final report to ICANN Board | 2019-11-07 | 2019-11-07 | SSR2-RT | 1 | 0%
| Publish final report | 2019-11-07 | 2019-11-07 | ICANN org | 1 | 0%
| Send Final Report to language services | 2019-11-07 | 2019-11-07 | ICANN org | 1 | 0%
| Implementation planning and feedback |  |  |  | 8 | 0%
| Complete ICANN organization survey on review process | 2019-11-07 | 2019-11-14 | SSR2-RT | 7 | 0%
| Identify one or two Review Team Members to remain available for clarification as may be needed during the planning phase of implementation of Review Team Recommendations. | 2019-11-07 | 2019-11-14 | SSR2-RT | 8 | 0%
| Face to Face meetings |  |  |  | 15.5
| #5 Washington DC | 2018-08-22 | 2018-08-24 | SSR2-RT | 3 | 100%
| #6 ICANN63 Barcelona | 2018-10-21 | 2018-10-24 | SSR2-RT | 2 | 100%
| #7 Los Angeles | 2018-01-25 | 2018-01-27 | SSR2-RT | 3 | 100%
| #8 ICANN64 Kobe | 2019-03-09 | 2019-03-14 | SSR2-RT | 3 | 0%
| #9 TBD (Europe) | 2019-05-17 | 2019-05-19 | SSR2-RT | 2.5 | 0%
| #10 ICANN65 Marrakech | 2019-06-24 | 2019-06-27 | SSR2-RT | 2 | 0%