Action Plan for Universal Acceptance of Domain Names and Email Addresses

FY22: July 2021 - June 2022

Introduction – UASG Communications Working Group

This document provides a summary of work accomplished based on UASG’s FY21 Action Plan.

Progress status indicators, as of 9 April 2021:

|  | Completed |
| --- | --- |
|  | In progress |
|  | Under planning or contracting |
|  | Not started |

FY21 Project Status

| # | Task | Budget (USD) | Status | Comment |
| --- | --- | --- | --- | --- |
| C1 | Develop Comms plan | 0 |  | In planning. |
| C2 | Develop comms for reaching out to Programming language library maintainers | 0 |  | UA Messaging document completed; being used in outreach. |
| C3 | Publish case studies with comms partner | 25,000 |  | In planning and progress. |
| C4 | Review and implementation UASG.tech website | 5,000 |  | In planning. |
| C5 | Organize a strategic comms partner – Edelman | 25,000 |  | Partner on-boarded and supporting comms work. |
| C6 | Maintain social media presence of UASG | 0 |  | Ongoing |
| C7 | Translation of relevant reports and case studies | 10,000 |  | Ongoing as requested by the community. |

FY22 Proposed Projects

| # | Task/Project | Budget (USD) | Description |
| --- | --- | --- | --- |
| C1 | Develop Strategic Comms Plan |  | Develop a strategic communications plan for the UASG/UA that will review and study objectives, key audiences, messaging and communications channels to reach the defined stakeholders |
| C2 | Content for communications channels: Explainer videos | 10,000 (estimated cost) | 3 explainer videos (animated), 1-2 mins explaining UA/EAI issues in English with subtitles in the 6 UN official languages |
| C3 | Organize a strategic comms partner – Edelman | 50,000 | UASG communications/content development and production (3-5 Blogs, 2-3 Case studies, etc.) and Ad-hoc support |
|  | Organize a strategic comms partner – Edelman: Newsletters, UA publications in mass media | ? | Develop UA Newsletters monthly; Develop 2-3 UA materials to publish in mass media (e.g. interviews, press releases) |
| C4 | Review and develop UA/EAI content/online materials |  | Review and develop content to support UASG, UA WGs activities and projects, for online channels (e.g. website, social media, UA community channels) |
| C5 | Translation of relevant reports and case studies | 10,000 |  |
| C6 | Maintain Social Media presence of UASG | 0 |  |
| C7 | Maintain UASG.tech website |  | Hosting service |
| C8 | Review and implementation of UASG.tech website | 5,000 |  |
| C9 | Reach-out and present the UASG/UA community in the national, regional IG forums/events |  |  |