## Slide 1: Universal Acceptance: Communications / Outreach Plan
11 December 2014
Name
Title, Division
Internet Corporation for Assigned Names and Numbers

## Slide 2
Situation Overview

## Slide 3
unpredictable
The Internet’s technical ‘rules’ are like a patchwork quilt:
Many applications and services we use everyday do not support new TLDs, which puts these TLDs at risk of being rejected by end users
*Analogy to be reviewed and potentially modified
Notes: The Internet’s technical ‘rules’ are a patchwork quilt; they have been developed differently and implemented inconsistently. The result is a fragmented, disparate experience for Internet users.
It’s important that the general public perceives new TLDs as reliable, competitive contenders in the Domain Name System. Registration of names must work, protocols must work, and services and applications impacting the user must work. Technical failures or shortcomings threaten to breed negative sentiment for new TLDs.
  Example: Donuts receiving complaints that they can’t use new gTLD email addresses in critical business and personal sites like banks and e-commerce sites.

## Slide 4
reliable
Universal Acceptance is like introducing a pattern into the Internet:
Top-level domains
Internationalized domain names
Internationalized email
    should be fully functional in all services and applications
*Analogy to be reviewed and potentially modified
Notes: Universal Acceptance is like a quilters pattern. It creates a reliable set of expectations for the Internet User based on 3 simple principles: TLDs, Internationalized Domain Names and internationalized email should be supported in all applications and services.
Many stakeholders in the Internet community have a vested interest in ensuring that all delegated TLDs, regardless of length, language or lifespan, are recognized and treated equally. ICANN is unique in that it has extensive, successful experience in administering the multistakeholder model. This experience will be required to draw all stakeholders together around a common purpose.

## Slide 5
Roles and Responsibilities
ICANN = Coordinator, Energizer
* Identifies relationships between ideas and people
* Concentrates group energy on forward movement
Internet Community = Initiator, Executor
* Proposes original ideas for solving issue
* Updates contracts and systems to work with new top-level domains and Internationalized email

## Slide 6
Objectives

## Slide 7
ICANN’s Universal Acceptance Roadmap
Primary goal: Inspire urgency
Educate stakeholders
Motivate and support action
Primary role: Facilitator/coordinator
Connect stakeholders
Track progress
Archive information
Notes: The Technical Services team has created a roadmap for how ICANN should approach the Universal Acceptance Initiative. The objectives for our communications efforts were established in this plan.
ICANN’s goal is to create a sense of urgency. We need to:
  Educate stakeholders about Universal Acceptance and why it matters
  Motivate stakeholders to take action
ICANN’s role is one of active coordination and facilitation. We need to:
  Connect stakeholders who are capable of helping one another remove technical obstacles
  Create a central repository of information and a system of record

## Slide 8
Communications / Outreach Goals
Educate stakeholders
Mobilize ICANN staff and community to drive awareness and participation
Motivate and support action
Persuade using individual benefits or greater good
Connect stakeholders
Nurture existing relationships, foster new ones
Track progress and archive information
Create a public system of record
Notes: The Communications and Outreach goals we set will support the Roadmap’s objectives.
Educate stakeholders
Mobilize ICANN staff and the communtiy to drive awareness and participation – we can not wait for (or expect) stakeholders to come to us
Motivate and support action
Explain what each stakeholder stands to gain from Universal Acceptance – personalize the communication to the business
Connect stakeholders
Learn what each stakeholder brings to the table and introduce them to one another strategically; nurture existing relationships
Track progress and archive information
Create a public system of record and communicate significant events to stakeholders

## Slide 9
Target Audiences – PLACEHOLDER
Phase I: Leaders
Domain Name Industry and Trade Associations
Phase II: Participants
Internet Service and Application Providers
Protocol and Operations Standards and Forums
Security Practitioners
Phase III: Interested Parties, Activists
Information Technology Practitioners
Educational Institutions
End User Communities
Notes: Who are we trying to reach and what is our engagement timeline? Communications recommends a 3-phase approach:
Phase I: Leaders
Audiences: Domain Name Industry and related trade associations
Rationale:
  The Industry need to get its house in order before it can turn around and demand change from other groups.
  Solid business cases for Universal Acceptance must be developed to help motivate Participants groups in Phase II.
Goals:
  Help them implement Universal Acceptance principles in their own systems and contracts
  Leverage those who achieve Universal Acceptance to reach new audiences
Sub-audiences:
  ICANN
  Registries (ccTLD & gTLD)
  Registrars
  Service Providers
Phase II: Participants
Audiences: Internet Service and Application Providers, Protocol and Operations Standards and Forums, Security Practitioners
Specific strategies to be determined
Phase III: Interested Parties, Activists
Audiences: Information Technology Practitioners, Educational Institutions, End User Communities
Specific strategies to be determined

## Slide 10
Strategy

## Slide 11
Define Universal Acceptance
Use “Universal Acceptance” in a sentence
Noun: Universal Acceptance means that all TLDs, IDNs and internationalized email work seamlessly
Adjective: ICANN is Universal Acceptance friendly
Verb: ICANN is modeling Universal Acceptance principles, ICANN has achieved Universal Acceptance
Why is it important?
One world, one Internet: Global top-level domain and email interoperability enable innovation for all.
Notes: Use “Universal Acceptance” in a sentence
How should we use the term Universal Acceptance in 3 of the basic building blocks of the English language: noun, adjective and verb form
Why is it important?
What theme should always be present in our messaging? This is the 30,000 foot view of why Universal Acceptance matters.
One world, one Internet: Global top-level domain and email interoperability enable innovation for all.

## Slide 12
Set the Tone
POSITIVE
Universal Acceptance is achievable. But it will require hard work. Help us build a better, more inclusive Internet. Global top-level domain and email interoperability enable innovation for all. There is much work to be done; we must start now!
REALISTIC
COLLABORATIVE
CONSCIOUS
URGENT
Notes: The tone will unify all of our messaging. Must be present in each communication.

## Slide 13
A Marathon, Not a Sprint
Multiple phases, tracks and techniques
Short and long term goals, interim metrics
Focus on the finish line
Notes: Universal Acceptance is a massive undertaking – our strategy is to approach it like running a marathon.
Multiple phases, tracks and techniques
Marathon training requires months of preparation; the only way to determine the right formula is to test, track and recalibrate along the way.
We will reach out to stakeholders in phases, categorized by their proximity to the issue and ability to make a difference.
Two tracks will be enacted simultaneously – one driven by the Technical Services team, and the second driven by the Communications team.
We will outline a variety of techniques in this plan, but adaptability will play an integral role in this initiative as we will inevitable learn new things over time.
Short and long term goals, interim metrics
Slow and steady wins the race! We have limited resources and we must use them carefully over time to avoid burn out.
Interim metrics will help us determine whether we’re on track to meet our short and long term goals.
Focus on the finish line
Like a marathon, the Universal Acceptance Initiative seems daunting.
We need to at all times remember the big picture, even as we break journey down in chunks with achievable milestones.

## Slide 14
Track 1: GDD Responsibilities
Enlist and mobilize evangelists
  Goal: Grow our network exponentially
  Step 1: Establish a Universal Acceptance Guidance Team
Establish timeline for ICANN to become Universal Acceptance friendly
Foster development of web presence
  ICANN site: provide educational materials and show progress of initiative
  Non-ICANN: content driven by Guidance Team
Notes: Enlist Evangelists
Create a Guidance Team with representative(s) from each stakeholder. Members should:
Be personally motivated to see Universal Acceptance come to fruition
Have influence in their field/industry.
Grow a list evangelists and check in with them frequently about their experiences and ideas. Perhaps hold a monthly meeting.
Establish timeline for ICANN to become Universal Acceptance friendly
We need a target date to work back from
Foster Development of a Web Presence
Universal Acceptance belongs to all seven stakeholder groups – therefore it requires neutral online territory.
ICANN should continue to populate the Universal Acceptance section of icann.org with educational materials, archive materials and initiative status reports.
We recommend that once created, the Guidance Team take the lead in creating a site dedicated entirely to Universal Acceptance. The group should consider all stakeholders when developing content and determining functionality, such as collaborative or social tools.

## Slide 15
Establish relationships with key trade associations One list per audience; make personal contact
Drive support for peer-to-peer communications Help participants collaborate with one another
Create a stratified participation model Let supporters choose their level of involvement
  Evangelists, Powerhouses, Contributors
Attend events Meet stakeholders on their turf
Track 1: GDD Responsibilities
Notes: Establish relationships with key trade associations
Create a list of associations for each stakeholder group. Reach out to each group personally and ask for them to provide information to their members.
Drive support for Person-to-Person Communications Methods
One of the objectives in the Roadmap is to connect others. Working with the Universal Acceptance Guidance Team, ICANN can determine the best tool or platform for making these types of introductions. This step may tie into the non-ICANN web presence development in terms of creating a collaborative work space.
Create Stratified Participation Model
Participation Ladder: Create experiences and participation opportunities for all of the following types of participants:
Observer – watches from afar, doesn’t add anything yet
Contributor – comments on their experience with Universal Acceptance
Powerhouse – companies invested in Universal Acceptance; willing to donate time and money
Evangelist – believes in UA and espouses its values to his/her community/followers, interacts directly with ICANN staff
Attend Events
Create a list of events relevant to each stakeholder group (ex. conferences, tradeshows etc.) and look for ways Technical Services team members can attend or participate (ex. sponsoring a booth).

## Slide 16
Create educational materials FAQs, one-pagers, talking points, presentations etc. that utilize tiered messaging
  Repackage content for use in all regions
Identify key press and industry analyst contacts Drive awareness and understanding of Universal Acceptance
Engage with press via interviews, contributed articles, informal/educational discussion etc. Discuss progress and highlight success stories
Track 2: Communications Responsibilities

## Slide 17
Facilitate development of a participant database Enable targeted messaging
Pursue speaking opportunities Gain multiple, in-person impressions
Conduct an internal educational program Teach engagement teams how to discuss externally
Consider Universal Acceptance certification A stamp of approval for companies to proudly display and further advertise the initiative
Track 2: Communications Responsibilities

## Slide 18
Distribute Universal Acceptance Playbook A how-to manual for companies
Social Monitoring & Outreach Follow the conversation and engage
Universal Acceptance Roadshow An educational workshop on how and why
University Collaboration Work with HR and other internal groups to establish an intern program
Track 2: Communications Responsibilities

## Slide 19
ICANN Resources
Global Domains Division
  Primary: Technical Services team, IDN team
  Secondary: Registry and Registrar Services teams
Global Communications
  Primary: GDD Communications team
  Secondary: Regional Communications leads
Senior ICANN Executives and Global Stakeholder Engagement Team

## Slide 20
Potential External Resources
Individuals / Entities / Industry Groups
  GDD Team Action: Continue to develop a list of potential participants representing a cross-section of stakeholder groups and required technical skill sets to drive execution of Universal Acceptance Roadmap

## Slide 21
High-level Messaging:
Track 2 (Communications) Phase I (Domain Name Industry)
Notes: All of the audiences outlined in ICANN’s Universal Acceptance Roadmap are actually stakeholders. Each has an interest in helping Universal Acceptance come to life, and all must work collaboratively to arrive at Universal Acceptance.
It’s up to ICANN to make a sound case, on both macro- and micro-levels, as to why each stakeholder group should not only participate in the Universal Acceptance Initiative, but make it a priority.
As mentioned earlier, our outreach priority (Phase I) is the Domain Industry and related trade associations. The following were provided by Ed in his Domain Name Industry outreach document.

## Slide 22
Educational Institutions
Don’t watch the industry evolve around you
Set the trend
Domain
Industry + Trade Associations
- EXAMPLE ONLY
Outreach Priority:
Phase I
Notes: The overall message to members of this group is “Be one of the first players in the industry with systems and contracts that fully recognize all TLDs.”
In the following slides we’ll discuss key messaging for each of the sub-groups in this category.

## Slide 23
Motivational Factor(s)
Universal Acceptance will affect the overall success of the New gTLD and IDN Programs
Messaging
Example: We must lead by example
ICANN – EXAMPLE ONLY
Notes: Starting with ICANN
ICANN has a financial and reputational stake in the expansion of generic Top-level Domains and its push to expand web usability via Internationalized Domain Names.
Lack of acceptance of new gTLDs and IDNs in systems and applications poses a major risk to their perceived success.
Achieving Universal Acceptance at ICANN puts our organization in a better position to motivate, compel and guide other stakeholders to do the same. Steps currently being undertaken include:
  Working with Legal to update contracts to require Universal Acceptance
  Working with vendors and internal developers to update operating systems so that they accept all TLDs

## Slide 24
Motivational Factor(s)
New top-level domains and Internationalized Domain Names are ripe with opportunity for new business, but they must work
Option: Include UA in contractual requirements
Messaging
Ex. Maximize potential for revenue growth
Ex. Universal Acceptance matures our industry
Registries (gTLD and ccTLD Operators) – EXAMPLE ONLY
Notes: Registries (gTLD and ccTLD Operators)
Public awareness of new gTLDs will only increase – but people outside of the tech community may not understand why these TLDs won’t work the way they expect them to (domain email addresses being rejected, idns rendering as A-Labels).
Ensuring new TLDs and IDNs are on an equal playing field with legacy TLDs is the only way to see full growth potential.
  Allow registrants to specify name servers and contact information (including email) using new top-level domains, IDNA2008 names, and Internationalized email addresses
  Systems used for business arrangements should comply with Universal Acceptance principals

## Slide 25
Motivational Factor(s)
TBD
Option: Ask registries to influence registrars
Messaging
Ex. TBD
Ex. Registries should work with registrars that support new TLDs and Internationalized Domain Names
Registrars – EXAMPLE ONLY

## Slide 26
Services
DNS hosting, Web hosting, Data Escrow, Dispute Resolution, Trademark Clearinghouse, Internet Protocol
Motivational Factor (TBD)
Example: Expansion of the DNS means more business
Messages (TBD)
Example: Helping new gTLDs succeed helps your bottom line
Service Providers – EXAMPLE ONLY
Notes: Service Providers
Service providers stand to gain from the increase in new gTLDs, meaning their success is directly tied to each provider’s success. The first step is for providers to update their own systems to accept all TLDs and next is to advocate for Universal Acceptance externally where possible.

## Slide 27
Work Status

## Slide 28
Tasks Completed
Development of Web Presence on ICANN.org
  Content:
    Explains what Universal Acceptance is
    Instructs viewer how to get involved
    Provides resources archive
  In progress: TLD acceptance issue reporting form
  Shortcut: http://www.icann.org/universalacceptance

## Slide 29
Next Steps: GDD - DRAFT
Assemble community-based Guidance Team
  Educate team on technical issues, importance of using common language and goals of initiative
  Help team establish leadership and direction
Prepare for ICANN 52
  Session and booth planning; networking opportunities
Finalize Universal Acceptance language for ICANN’s external vendors

## Slide 30
Next Steps: Communications DRAFT
Develop tactical plan for Domain Name Industry outreach
Create educational materials
  Fact sheets for each stakeholder group
Prepare for ICANN 52
  Collaborate on session / booth planning
  Create plan for populating Guidance Team

## Slide 31
Timeline: Phase I Outreach/Comms (DRAFT)
2014 |  | 2015 |  |  | 
 | Q4 | Q1 | Q2 | Q3 | Q4
Track 1 (GDD) |  |  |  |  | 
Track 2 (Comms) |  |  |  |  | 
Guidance Team + Evangelists
Community UA Web Presence
Participant Database
Participation Model
Attend Events
Educational Materials
Domain Name Industry/Trade Outreach
Speaking Opportunities
Internal Education
Social Media Monitoring/Outreach
Universal Acceptance Playbook
Peer to Peer Comms
Notes: COMMS Tasks for Late 2015 / 2016:
Universal Acceptance Certification Program
Universal Acceptance Roadshow
University Collaboration
Press Engagement – need to have some examples of success to make this attractive to News Media