## FY20 Prioritization Matrix
UASG FY20 Action Plan
Answer for (UP) Under Planning and (NS) Not-Started projects only
ID | Project | Status | Budget Allocated | (1) Is the project still relevant? | If (1) is 'No' or 'Maybe' Please explain your answer | If (1) is 'Yes' Please respond; Can the project be completed in FY20? | If project cannot be completed in FY20, please list reasons; if WG recommends carrying the project into FY21, please state this | Priority FY20 | Observations (e.g. List final product for Complete projects)
C1 | Develop a Communication Strategic Plan and associated deliverables Output = Communications Strategic Plan (incorporate in Strategic Communications Partner task) | UP |  | Yes |  | ongoing |  | FY21 | Yes, develop a plan and maintain it as we move forward; review quarterly;
C2 | Commission independent and expert audience identification research and tested messaging and channels - Identify characteristics of most receptive audiences in the software development communities - Industry, Geography, Position Output = Receptive Audience Characteristics (Kobe A.1) | NS | Yes
C3 | Commission independent and expert audience research of most receptive messages Output = Refined Messaging (Kobe A.1) | UP | Yes
C4 | Commission independent and expert audience research to Identify most responsive channels of reaching these audiences | NS | Yes
C5 | Prepare at least six Case Studies on different types of organizations who have pursued Universal Acceptance. At least three should be outside the IT Industry Output = Six Case Studies | IP |  |  |  | ongoing |  | FY21 | Have a strategy to communicate these case studies effectively
C6 | Organize UA Day. - Develop detailed characteristics of content, audience purpose, expectations and measures of success. - Organize invitations and encourage participation - Organize the logistics for the event - Promote pre- and post event. - Publish the Proceedings of the UA Day Output = UA Day | NS | Yes
C7 | Oversee the regular review of all UASG published documents and research report. Update as appropriate | IP | Yes
C8 | Review the content and structure of the UASG.tech website on an annual basis. | IP | Yes
C9 | Fund hosting and maintenance of the UASG website | C | Yes
C10 | Continue UASG Leadership program without spending funds on program development or awards. | NS
C11 | Produce materials (printing, design) | IP | Yes
C12 | Organize Strategic Communications Partner Activities will include media engagement, strategic and tactical advice, content creation (currently Edelman). | C | Yes
C13 | An annual research into audience specific interests. This will assist in the development of materials as well as provide information for Media releases. Output = Topics for Research Output = At least 10 media campaigns. | NS | Yes
C14 | Provide support and encouragement for Global and Regional IGFs and Schools of Internet Governance. Funds will cover travel and printed materials. Arranging UA into the workshop in each event will be the responsibility of the Secretariat. | C | Yes
C15 | Organize regular meetings of the UA Ambassadors - Monthly virtual meetings and one face-to-face meeting each year to be held in conjunction with an event where several Ambassadors might normally attend. (Kobe E.2) | C | yes
C16 | Manage a calendar of events for use by the UASG Community as a whole and the UA Ambassadors and Communication Working Group (Kobe E.3) | UP
C17 | Social Media: The UASG to maintain a social media presence in Twitter, LinkedIN, Facebook, WhatsAPP, GitHub and Stack Overflow. (incorporate in Strategic Communications Partner task) | C
C18 | Social Media - Active Engagement. Instead of creating posts and letting them be, this would involve someone being an active participant in discussions. This will be particularly useful in the technical platforms such as GitHub and StackOverflow and such. (incorporate in Strategic Communications Partner task) | UP
C19 | Leveraging ICANN’s Global communications team, the UASG will look to have at least 6 media messages, for each region, each year. Resources to be secured from ICANN’s Global Communications Team | IP
C20 | Translation of content, including relevant reports and case studies, in languages identified | IP | Yes
Note on C3: C: Complete IP: In Progress UP: Under Planning NS: Not Started
Note on D3: Yes No
Note on I3: To be filled by Coordination Group FY20 = Complete in FY20 FY21 = Consider for FY21 Stop = Stop