## FY20 Prioritization Matrix
UASG FY20 Action Plan
Answer for (UP) Under Planning and (NS) Not-Started projects only
ID | Project | Status | Budget Allocated | (1) Is the project still relevant? | If (1) is 'No' or 'Maybe' Please explain your answer | If (1) is 'Yes' Please respond; Can the project be completed in FY20? | If project cannot be completed in FY20, please list reasons; if WG recommends carrying the project into FY21, please state this | Priority FY20 | Observations (e.g. List final product for Complete projects)
E1 | Oversee the review or development of training material for EAI EAI Training for Email administrators Detailed training for Email software providers Overview of EAI for managers and policy makers Output = Training material including documentation, slides and online training material. Training to be organized and managed by EAI Working Group
E1.1 | EAI Training for Email Admins | C | Yes |  |  |  |  | FY20 | EAI training for Email administrator (currently with ICANN comms for formatting)
E1.2 | EAI Training for Software providers | NS |  | Yes |  | FY21 |  | FY21 | Rescoping and prioritizing to maximize impact during the time of social distancing. To be considered when we restart this in FY21.
E1.3 | EAI Training for Managers and Policy Makers | NS |  | Yes |  | FY21 |  | FY21 | Rescoping and prioritizing to maximize impact during the time of social distancing. To be considered when we restart this in FY21.
E2 | Oversee the EAI Evaluation Efforts - Output = Include as part of Annual report and stand-alone evaluation report | C | Yes |  |  |  |  | FY20 | Email Address Internationalization (EAI): Evaluation of Major Email Software and Services (UASG021B) UASG021C is In-Progress, the SOW is out for bidding
E3 | Keep a registry of email software and service providers and their EAI status - updated ongoing basis Output = maintained registry | [7 empty] | E3 includes a public part and confidential part.
E3.1 | Inventory of software w/EAI status | IP |  | Yes |  | FY20 | Maintaining the registry is an on going work. | FY20 | Inventory of Email Tools (Calling for Proposal)
E3.2 | Contact List of Developers | NS |  | Yes |  | FY21 | Maintaining the registry is an on going work. | FY21
E4 | Experience EAI with Free email accounts | NS |  | Yes |  |  |  |  | E4 is relevant but will be merge into E3: important to ensure the people can find EAI free account providers in their local community.
Note on C3: C: Complete IP: In Progress UP: Under Planning NS: Not Started
Note on D3: Yes No
Note on I3: To be filled by Coordination Group FY20 = Complete in FY20 FY21 = Consider for FY21 Stop = Stop