## ATRT1
ATRT1 Recommendations | Implementation Assignments |  | F. Percentage/portion that is complete? | G. Does s/he believe ICANN fully implemented the recommendation? If not, why not? If not, what parts were not implemented, and why not? | I. Did s/he identify additional opportunities for improvement by virtue of the implementation of these recommendations? | J. What has been the outcome and effect both inside ICANN and external to ICANN as a result of the implementation of the recommendation? | L. How does s/he feel that ICANN has improved as a result of the implementation of the recommendation? | N. In view of ATRT1 what changes in workflows and/or organization where undertaken? | ATRT2 Recommendation? | Discussion | Actions | Conclusions
Measuring Success 9.1 (d)
27. Evaluate and report on progress on recommendations and accountability & transparency commitments in the AoC. | Board/Exec | Steve Crocker
| Staff: Office of the CEO | Denise Michel | Please see 2012 Implementation Summary re: ATRT Rec. No. 27 (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf). | Please see 2012 ATRT Implementation Summary (www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf) and the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) The implementation plan, as amended, was fully implemented. The Board & Staff regularly evaluated progress against the ATRT1 recommendations, and the accountability and transparency commitments in the AoC, and in general considered the accountability and transparency performance of the whole organization. Regular reports were publicly issued on ATRT1 implementation and the public was kept apprised of ICANN activities on a myriad of efforts broadly aimed at improving accountability and transparency. | Additional opportunities include: agreeing on a definition of "public interest," "accountability" and "transparency;" developing and reporting on additional metrics and benchmarks related to ATRT1 recommendations; expanding a public "dashboard "reporting on accountability and transparency-related activities; conducting an organization-wide assessment of ICANN's performance against accountability and transparency commitments. | Public reporting reinforced Board and Staff attention to ATRT1 implementation. Presumably public confidence on ATRT1 implementation was increased, but this was not quantified. | See J. Additional information is available in the 2012 Annual Report on ATRT Implementation (http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf) | NA | Metrics needed | Brian:metrics can improve communications. How it's communicated is a real opportunity. Brian: Effectiveness needs to be addressed - data vs. information - How do you communicate this important work - at ICANN meeting, via Chairman's blog, other? Board and staff should have a role.

## Reference Materials
Reference Materials
Document | Link
Accountability & Transparency Review Team 1 (ATRT1) Final Report and Recommendations, January 2010 | https://www.icann.org/en/about/aoc-review/atrt/final-recommendations-31dec10-en.pdf
ATRT Recommendations - Proposed Implementation Plans; Ocotber 2011 | http://www.icann.org/en/news/in-focus/accountability/atrt-recommendations-implementation-plans-08feb12-en.pdf
ATRT Implementation Summary Report 2012 | www.icann.org/en/news/in-focus/accountability/atrt-project-list-workplans-29jan13-en.pdf
2012 Annual Report - Implementation of the Accountability & Transparency Review Team Report; January 2013 | http://www.icann.org/en/news/in-focus/accountability/atrt-implementation-report-29jan13-en.pdf
NomCom web site | http://nomcom.icann.org/
ICANN 2012 NOMCOM FINAL REPORT | http://nomcom.icann.org/nomcom-final-report-08oct12-en.pdf
Adopted Board Resolution - Chair Remuneration, August 2013 | http://www.icann.org/en/groups/board/documents/resolutions-05aug10-en.htm#5
Community Input Advice Framework, September 2012 | www.icann.org/en/news/in-focus/accountability/input-advice-function-24sep12-en.pdf
Policy vs. Implementation Public Comment Period, January 2013 | http://www.icann.org/en/news/public-comment/policy-implementation-31jan13-en.htm
ICANN Accountability & Transparency | http://www.icann.org/en/news/in-focus/accountability
FY12 Operating Plan and Budget Fiscal Year Ending 30 June 2012, adopted 24 June 2011 | http://www.icann.org/en/financials/adopted-opplan-budget-fy12-09sep11-en.pdf
GAC High Level Meeting, Toronto - October 2013 | http://toronto45.icann.org/gac-hlm
JWG Final Report & Public Comment Forum, July 2011 | http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm
Revised GAC Operating Principles | https://gacweb.icann.org/display/gacweb/Core+Principles
Publication of what constitutes GAC advice, July 2011 | http://www.icann.org/en/news/announcements/announcement-07jul11-en.htm