## Sheet1
Recommendation | Summary of ICANN’s assessment of implementation including actions taken, implementability and effectiveness | Summary of community input on implementation, including effectiveness | ATRT2 analysis of recommendation implementation (e.g. complete, incomplete or ongoing) | ATRT2 assessment of recommendation effectiveness
Strategic Priority
1. WHOIS, in all its aspects, should be a strategic priority, form the basis of staff incentivization (including CEO’s) and organizational objectives; Board should create a committee that includes the CEO to be responsible for priority and key actions; issue public updates on progress against targets for all aspects of WHOIS. | WHOIS is deemed to be a strategic focus. Compliance restructured and reports to CEO. ICANN reported that in May, implementation was 25% complete. | Most parts of the community have been silent on this. Advocates for At-Large have not been satisfied that the changes are effective and not merely show, supported by the lack of replies to specific queries. | It is unclear how to assess to what extent the changes are effective. There is clearly a focus on long term WHOIS replacement, but ongoing status is far less clear. Monthly Contractual Compliance reports are not sufficiently clear as to create a clear understanding. | Ditto.
Single WHOIS Policy
2. Board should oversee creation of a single WHOIS policy document, and reference it in agreements with Contracted Parties; clearly document the current gTLD WHOIS policy as set out in the gTLD Registry & Registrar contracts & Consensus Policies and Procedure. | The Board Briefing Document noted the lack of a single policy (whe WHOIS RT's conclusion) and said "These presently available conditions and policies should be publicly available from one source." The result, which is deemed to completely satisfy the recommendatiion, can be viewed at http://www.icann.org/en/resources/registrars/whois-policies-provisions, entitled "Single Webpage for ICANN Whois-Related Policies and Provisions" but is largely a vast set of pointers to various policy documents and contractual terms. | There was no community input other than from the WHOIS RT which considered the result to not meet their original intent. | The ATRT concurs with the WHOIS RT assessment. | The implementation would be of use to a lawyer or Contractual Compliance employee by narrowing down the number of documents to be consulted. It is of minimal use to others.
Outreach
3. ICANN should ensure that WHOIS policy issues are accompanied by cross community outreach, including outreach to the communities outside of ICANN with a specific interest in the issues, and an ongoing program for consumer awareness.
Compliance
4. ICANN should ensure that its compliance function is managed in accordance with best practice principles, including full transparency on resourcing and structure; provide annual reports; appoint a senior executive whose sole responsibility would be to oversee and manage ICANN’s compliance function (reporting to Board Committee); provide all necessary resources to manage and scale compliance team’s activities.
Data Accuracy
5. ICANN should ensure that the requirements for accurate WHOIS data are widely and proactively communicated, including to current and prospective Registrants, and should use all means available to progress WHOIS accuracy, including any internationalized WHOIS data, as an organizational objective.
6. ICANN should take appropriate measures to reduce the number of WHOIS registrations that fall into the accuracy groups “Substantial Failure and Full Failure” (as defined by the NORC Data Accuracy Study, 2009/10) by 50% within 12 months and by 50% again over the following 12 months.
7. ICANN shall produce and publish an accuracy report focused on measured reduction in WHOIS registrations that fall into the accuracy groups “Substantial Failure and Full Failure” on an annual basis.
8. ICANN should ensure that there is a clear, unambiguous and enforceable chain of contractual agreements with registries, registrars, and registrants to require the provision and maintenance of accurate WHOIS data; agreements should ensure that clear, enforceable and graduated sanctions apply to registries, registrars and registrants that do not comply with its WHOIS policies; sanctions should include de-registration and/or deaccreditation in cases of serious or serial noncompliance.
9. Board should ensure that the Compliance Team develop metrics to track the impact of the annual WHOIS Data Reminder Policy (WDRP) notices to registrants; metrics should be used to As per (1) above, the Board will initiate a policy on the purpose of the gTLD WHOIS service, and this will help drive the principles behind privacy/proxy develop and publish performance targets, to improve data accuracy over time; if this is unfeasible, Board should ensure that an alternative, effective policy is developed and implemented that achieves the objective of improving data quality, in a measurable way.
Data Access – Privacy and Proxy Services
10. ICANN should initiate processes to regulate and oversee privacy and proxy service providers; processes should be developed in consultation with all interested stakeholders and note relevant GNSO studies; a possible approach to achieving this would be to establish an accreditation system for all proxy/privacy service providers, and consider the merits (if any) of establishing or maintaining a distinction between privacy and proxy services; goal is to provide clear, consistent and enforceable requirements for the operation of these services consistent with national laws, and to strike an appropriate balance between stakeholders with competing but legitimate interests -- including privacy, data protection, law enforcement, the industry around law enforcement and the human rights community. A list of objectives for regulation is provided for consideration, including: labeling WHOIS entries made by a privacy or proxy service; providing full WHOIS contact details for the privacy/proxy service provider; adopting agreed standardized relay and reveal processes and timeframes; Registrars should disclose their relationship with any proxy/privacy service provider; maintaining dedicated abuse points of contact for each provider; conducting periodic due diligence checks on customer contact information; maintaining the privacy and integrity of registrations in the event that major problems arise with a privacy/proxy provider; and providing clear and unambiguous guidance on the rights and responsibilities of registered name holders, and how those should be managed in the privacy/proxy environment.
Data Access – Common Interface
11. It is recommended that the Internic Service is overhauled to provide enhanced usability for consumers, including the display of full registrant data for all gTLD domain names (whether those gTLDs operate thin or thick WHOIS services); operational improvements should include enhanced promotion of the service to increase user awareness.
Internationalized Domain Names
12. ICANN should task a working group within six months of publication of this report, to determine appropriate internationalized domain name registration data requirements and evaluate available solutions; at a minimum, the data requirements should apply to all new gTLDs, and the working group should consider ways to encourage consistency of approach across the gTLD and (on a voluntary basis) ccTLD space; working group should report within a year.
13. The final data model, including (any) requirements for the translation or transliteration of the registration data, should be incorporated in relevant Registrar & Registry agreements within 6 months of Board adoption of working group’s recommendations, or put explicit placeholders in the new gTLD program agreements, & in existing agreements when they come up for renewal.
14. Metrics should be developed to maintain and measure the accuracy of the internationalized registration data and corresponding data in ASCII, with clearly defined compliance methods and targets.
Detailed and Comprehensive Plan
15. ICANN should provide a detailed and comprehensive plan within 3 months after the submission of the Final WHOIS Review Team report that outlines how ICANN will move forward in implementing these recommendations.
Annual Status Reports
16. ICANN should provide at least annual written status reports on its progress towards implementing the recommendations of this WHOIS Review Team. The first of these reports should be published one year, at the latest, after ICANN publishes the implementation plan mentioned in recommendation 15, above.